## Phase 2 Overview
ErgonX Phase 2 — Concept-to-Implementation Register
Purpose: convert approved UI concepts into an implementation roadmap without allowing concept screens to silently redefine ErgonX business rules.
Area | Decision / Rule | Phase 2 Direction | Priority | Owner Type | Status | Key Dependency | Notes
Security MFA | Use TOTP + email OTP only; no SMS OTP until a reliable provider exists. | Implement governed email OTP challenge flow, rate limits, expiry and audit events. | P0 | Platform/Security | Approved | Email delivery | Do not expose recovery-phone features yet.
Executive Dashboard | For Institution Admin and Director/CEO/equivalent executive users. | Strategic institution-wide dashboard; module-aware and permission-driven. | P1 | Analytics/Platform | Approved | Cross-module metrics | Authorize via permission such as dashboard.executive.view, not hard-coded role string only.
Insights | For all other authorized operational/admin roles. | Permission-filtered cross-module analytical workspace. | P1 | Analytics/Platform | Approved | Reporting services | Standard Employee lands on Employee Home unless separately granted analytical access.
Expenses | Expenses is a current Accounting capability. | Deepen into employee claim → approval → finance review → journal → settlement workflow. | P1 | Accounting | Approved | Approvals + GL mappings | No hard delete after approval/posting.
Phase | Project is now entering Phase 2. | Concepts become target direction after architectural review. | P0 | All | Approved | Implementation register | Phase 2 includes selected functional expansion, not just visual migration.
Architecture | Modular monolith + tenant-aware institution boundary remains authoritative. | Extend existing contracts rather than replacing them. | P0 | Platform | Locked | Existing backend contracts | Stitch is visual authority; backend/domain rules are functional authority.
Governed Records | Sensitive records follow lifecycle, approval, audit, correction/reversal rules. | Formalize shared governed-record pattern across modules. | P0 | Platform/Domain | Approved | Audit + approvals | Shared conventions, domain-specific states.

## Screen Register
ID | Concept Screen | Module / Surface | Existing Route / Likely Route | Current Support | New / Expanded Capability | Backend Work | Frontend Work | Permissions / RBAC | Audit / Governance | Dependencies | Phase 2 Wave | Priority | Implementation Decision | Acceptance Criteria
SCR-001 | Login | Authentication | /login | Supported | Visual redesign only; retain password + MFA flow | Minimal | Implement approved responsive auth screen | Public auth flow | Login/MFA audit | BFF auth | Wave 1 | P0 | Implement | No role-specific login pages; valid auth flows preserved.
SCR-002 | Workspace splash / initialization | Platform shell | /loading or transient state | Partial | Tenant/membership/module resolution loading state | Expose readiness/context load status if needed | Implement non-artificial splash | Authenticated | No special audit | Auth + institution resolution | Wave 1 | P1 | Implement | Displays only during real initialization; no artificial delay.
SCR-003 | Institution registration | Onboarding | /register | Partial | Institution + first admin registration | Validate institution/admin payload; onboarding creation | Implement split institution/admin form | Public create-org permission boundary | Account + institution creation audit | Onboarding | Wave 3 | P1 | Implement | Creates institution, admin identity, onboarding state; terms acceptance stored if required.
SCR-004 | Home workspace | Home | /home | Supported | Role-aware quick actions, recent work, needs attention, weekly snapshot | Aggregate existing module summaries | Recompose Home per concept | Permission-filter each card/action | Activity events where available | Modules + permissions | Wave 3 | P1 | Implement | No invented metrics; disabled modules disappear.
SCR-005 | Executive Dashboard | Executive | /executive | Partial | Strategic cross-module executive metrics | Cross-module aggregation endpoints | Implement dashboard visual system | dashboard.executive.view | Read events optional; source data audited at module level | HR + Payroll + Accounting + Reports | Wave 3 | P1 | Implement | Institution Admin/Director/CEO only by effective permission; module-aware.
SCR-006 | Insights | Analytics | /insights | Partial | Operational analytics for non-executive authorized roles | Permission-filtered analytical queries | Implement role-aware tiles/charts | analytics.insights.view + source perms | Source data only | Reports/Analytics | Wave 3 | P1 | Implement | All non-executive authorized roles see only permitted module data.
SCR-007 | HR Dashboard | HR | /hr/dashboard | Supported | Headcount trends, quick actions, needs attention, upcoming | Aggregate current HR metrics | Rebuild against Design System v2 | HR dashboard permission | Source actions audited | Employees + Recruitment + Leave + Attendance | Wave 3 | P1 | Implement | Metrics derive from authoritative records; no placeholders in production.
SCR-008 | Employee directory | HR | /employees | Supported | KPI strip, configurable columns, side preview, invite employee | Maybe add lightweight preview API/fields | Implement table, filters, side panel | employee.view / employee.create / invite | Edits/invites audited | Employee + Membership | Wave 3 | P1 | Implement | Preview respects field-level access and self-edit restrictions.
SCR-009 | Employee detail | HR | /employees/:id | Supported | Richer tabs: employment, compensation, attendance/leave, payroll, documents, history | Expose aggregate/detail endpoints as needed | Implement richer detail IA | Granular employee/comp/payroll perms | All admin changes audited | HR + Payroll + Attendance + Docs | Wave 3 | P1 | Implement | Administrative users cannot edit own protected HR record using admin powers.
SCR-010 | Employee lifecycle controls | HR | /employees/:id | Partial | Deactivate, offboard, archive, restore, lifecycle-aware actions | Lifecycle actions + retention rules | Implement action menu and lifecycle panel | employee.deactivate/offboard/archive | Mandatory lifecycle audit | Governed Record Pattern | Wave 3 | P1 | Implement | No hard delete for referenced employee records.
SCR-011 | Recruitment dashboard / pipeline | Recruitment | /recruitment | Supported/Partial | Pipeline stages, metrics, create requisition | Extend pipeline aggregates | Implement stage board | recruitment.view/manage | Stage changes audited | Recruitment entities | Wave 4 | P1 | Implement | Stages reflect configured recruitment stages and real records.
SCR-012 | Create job requisition | Recruitment | /recruitment/requisitions/new | New | Job requisition domain before posting | Add JobRequisition, hiring plan, approval link | Implement wizard/form | requisition.create | Create/submit/approval audited | Approval engine | Wave 4 | P1 | Implement | Requisition can be drafted, submitted, approved, published/converted to posting.
SCR-013 | Job requisition detail | Recruitment | /recruitment/requisitions/:id | New | Requisition lifecycle, hiring team, approvals, audit | Requisition detail + team + lifecycle APIs | Implement detail page | requisition.view/manage/approve | Full history | JobRequisition + approvals | Wave 4 | P1 | Implement | Approval required before publish when configured.
SCR-014 | Candidate detail / scorecard | Recruitment | /recruitment/candidates/:id | Partial | Structured scorecards, documents, activity | Evaluation template/criteria/score models | Implement scorecard UX | candidate.view/evaluate | Evaluation submissions audited | Recruitment | Wave 4 | P1 | Implement | Criteria configurable per role/requisition; evaluators scoped.
SCR-015 | Interview scheduling | Recruitment | /recruitment/interviews/new | Partial | Timezone, panel, agenda, invitation preview | Base scheduling APIs; no live calendar availability initially | Implement scheduler without fake availability | interview.manage | Schedule/reschedule audited | Email notifications | Wave 4 | P1 | Implement base | External calendar/Teams availability deferred to integration wave.
SCR-016 | Offer lifecycle | Recruitment | /recruitment/offers/:id | Supported/Partial | Draft→Approval→Sent→Accepted/Declined, offer letter, response | Extend offer lifecycle, approvals, response | Implement lifecycle page | offer.manage/approve/send | Offer changes audited | Approvals + documents | Wave 4 | P1 | Implement | Accepted offer can trigger governed hire conversion.
SCR-017 | Application history & lineage | Recruitment | /recruitment/applications/:id/history | New/Partial | Immutable application history and successor Employee record | Record lineage / linked-record APIs | Implement lineage/timeline UI | application.view_history | Mandatory | Governed Record Pattern | Wave 4 | P1 | Implement | Converted application remains read-only with successor Employee link.
SCR-018 | Public application wizard | Recruitment | /careers/... | New | External candidate portal/application draft | Public auth/privacy/upload surface | Implement later | Public candidate permissions | Consent + submission audit | Public careers portal | Wave 8 | P2 | Phase 2 later | Do not expose until security, privacy and candidate identity model are complete.
SCR-019 | Leave dashboard | Leave | /leave | Supported | Trends, calendar, policy alerts, approvals | Aggregate policy/leave metrics | Implement dashboard | leave.view/manage | Source actions audited | Leave policies | Wave 3 | P1 | Implement | Policy alerts distinguish PASS/FAIL/WARNING/NOT_EVALUATED.
SCR-020 | Request Leave | Self-Service / Leave | /my-workspace/leave/request | Supported/Partial | Half-day, working-day calculation, draft, attachments, route preview | Extend request fields/working-day engine if needed | Implement form | leave.create_own | Submit/change audit | Leave types + approvals | Wave 3 | P1 | Implement | Required supporting documents enforced by configured policy.
SCR-021 | Leave Request Review | Leave | /leave/requests/:id/review | Partial | Team availability, comments, delegate, request changes, history | Review endpoint + comments + delegation | Implement review workspace | leave.approve/delegate | Decisions/comments audited | Approval engine | Wave 3 | P1 | Implement | Unavailable policy data is not represented as compliant.
SCR-022 | Attendance dashboard | Attendance | /attendance | Supported/Partial | Rate, lateness, missing punches, adjustment queue, exceptions | Aggregate metrics and exception queries | Implement dashboard | attendance.view/manage | Source changes audited | Attendance records | Wave 3 | P1 | Implement | Metrics must use defined period and schedule logic.
SCR-023 | My Attendance | Self-Service / Attendance | /my-workspace/attendance | Supported/Partial | Calendar, daily records, adjustment request | Self-service summary APIs | Implement page | attendance.view_own / adjustment.create_own | Adjustment requests audited | AttendanceAdjustment | Wave 3 | P1 | Implement | Only own records; no organization-level data.
SCR-024 | Attendance adjustment review | Attendance | /attendance/adjustments/:id | New/Partial | Evidence, scheduled vs recorded vs requested, policy checks, delegate/request changes | AttendanceAdjustment + evidence + validation | Implement review page | attendance.adjustment.review | Full timeline audit | Approvals + schedules + leave | Wave 3 | P1 | Implement | Finalized payroll periods trigger governed downstream correction, not silent rewrite.
SCR-025 | Payroll workspace | Payroll | /payroll | Supported/Partial | Run lifecycle, approvals, compliance checks, related actions | Extend lifecycle/summary endpoints | Implement workspace | payroll.view/manage | Lifecycle audited | Payroll engine | Wave 5 | P1 | Implement | States reflect backend run status; 'Paid' does not imply bank transfer unless recorded.
SCR-026 | Payroll run detail / exceptions | Payroll | /payroll/runs/:id | New/Partial | Structured validation exceptions with severity/blocking status | PayrollValidationRule + PayrollException | Implement exceptions tab | payroll.resolve_exception | Resolution and progression audited | Ghana preset + employee/pay data | Wave 5 | P0 | Implement | Blocking exceptions prevent approval/finalization.
SCR-027 | My Payslips | Self-Service / Payroll | /my-workspace/payslips | Supported | Year filter, secure preview/download | Maybe status/detail contract refinements | Implement page | payslip.view_own | Download audit optional | Payroll | Wave 3 | P1 | Implement | Only finalized/available payslips can be opened/downloaded.
SCR-028 | Accounting dashboard | Accounting | /accounting | Supported/Partial | Exceptions, approvals, unposted journals, close status, cash flow, controls | Aggregated accounting health endpoints | Implement dashboard | accounting.dashboard.view | Source data audited | GL/AP/AR/Bank | Wave 6 | P1 | Implement | Close status only shown if period-close model exists.
SCR-029 | General Ledger | Accounting | /accounting/general-ledger | Supported | Hierarchical COA, journal table, account panel | Expose tree/account details as needed | Implement 3-pane layout | gl.view/journal.create | Journal actions audited | COA + journals | Wave 6 | P1 | Implement | Posted journals remain immutable; balance backend authoritative.
SCR-030 | Journal Entry Detail | Accounting | /accounting/journals/:id | Supported/Partial | Related records, attachments, approval, audit events | Add attachments/links if missing | Implement detail page | journal.view/manage/post | Mandatory journal audit | Approvals + documents | Wave 6 | P1 | Implement | Debit = credit enforced server-side; posted edits prohibited.
SCR-031 | Accounts Payable | Accounting | /accounting/ap | Supported/Partial | Approval queue, vendor summary, bill filters | AP queue/summary endpoints | Implement list/queue | ap.view/manage/approve | Bill lifecycle audited | Vendors + approvals | Wave 6 | P1 | Implement | Purchase Orders not required for this wave.
SCR-032 | Vendor Bill Detail | Accounting | /accounting/ap/bills/:id | Supported/Partial | Document viewer, payment status, approval route, attachments | Extend document/settlement metadata | Implement detail page | ap.bill.view/manage | Bill/pay status changes audited | Documents + payments | Wave 6 | P1 | Implement | Scheduling payment must not imply actual bank transfer.
SCR-033 | AP bulk actions | Accounting | /accounting/ap | New | Governed bulk archive/approval/adjustment/cancel with dependency checks | Batch job + eligibility service | Implement action drawer | ap.bulk_* perms | Per-record + batch audit | Background jobs | Wave 7 | P2 | Implement later | Partial success reported explicitly; finalized/paid records protected.
SCR-034 | Accounts Receivable | Accounting | /accounting/ar | Supported/Partial | Aging, upcoming receipts, reminders, customer controls | Add AR aging/collection summaries | Implement list/dashboard | ar.view/manage | Invoice/payment actions audited | Customers + invoices | Wave 6 | P1 | Implement core | Automated dunning deferred.
SCR-035 | Customer Invoice Detail | Accounting | /accounting/ar/invoices/:id | Supported/Partial | Document viewer, collections, payment, credit/void, reminders, related docs | Extend invoice lifecycle and payment history | Implement detail page | ar.invoice.manage | Mandatory | AR + documents | Wave 6 | P1 | Implement core | Void/credit actions governed; reminders manual initially.
SCR-036 | Expenses / My Expenses | Accounting + Self-Service | /accounting/expenses and /my-workspace/expenses | Supported but deepen | Employee claim→approval→finance review→journal→settlement | ExpenseClaim/Item/Attachment/Policy/Mapping enhancements | Implement admin + self-service flows | expense.* granular perms | Full lifecycle audit | Approvals + GL + docs | Wave 6 | P0 | Implement | No hard delete after approval/posting; mappings configurable, not hard-coded.
SCR-037 | Bank Reconciliation | Accounting | /accounting/bank-reconciliation | New/Partial | Statement import, match/unmatched, reconciliation sessions | BankStatement/Line/ReconciliationSession/Match | Implement workspace | bank.reconcile | Full reconciliation audit | Bank accounts + GL | Wave 7 | P1 | Implement manual/import-based | Bank feeds and auto-match providers later.
SCR-038 | Bank Reconciliation Session Detail | Accounting | /accounting/bank-reconciliation/:id | New | Progress, statement balances, transaction matching | Session detail/match APIs | Implement detail table | bank.reconcile | All matches/unmatches audited | Reconciliation models | Wave 7 | P1 | Implement | Completion requires reconciliation invariants.
SCR-039 | Budgets | Accounting | /accounting/budgets | New | Fiscal period + departmental budget management | Budget/BudgetLine/BudgetRevision models | Implement budget workspace | budget.view/manage/approve | Budget revisions audited | GL dimensions | Wave 7 | P2 | Implement after core accounting | Committed amount omitted until legitimate commitment source exists.
SCR-040 | Budget Detail | Accounting | /accounting/budgets/:id | New | Allocated/actual/remaining/variance, approval history | Budget reporting API | Implement detail | budget.* | Mandatory | Budgets + GL | Wave 7 | P2 | Implement after base | Actual comes only from posted GL.
SCR-041 | Financial Reports library | Accounting | /accounting/financial-reports | Partial | Report library, standard/custom/management/compliance categories | Report metadata/catalog | Implement library | financial_report.view/create | Run/export events audited | Reporting | Wave 7 | P2 | Implement staged | Do not promise XLSX/PDF until backend support exists.
SCR-042 | Statement of Financial Position | Accounting | /accounting/financial-reports/:id | Partial | Formal statement preview, parameters, versions, access | Statement generation/mapping | Implement report detail | financial_report.run | Generation/version audit | COA classifications | Wave 7 | P2 | Implement standard reports | Comparatives only from authoritative posted periods.
SCR-043 | Reports & Analytics catalogue | Reports | /reports | Partial | Dashboards/reports catalogue, ownership, sharing, freshness, scheduled reports | Report metadata + sharing models | Implement catalogue | report.view/share/manage | Share/publish audited | Reporting service | Wave 8 | P2 | Implement staged | Start with catalogue + saved configs before generic report builder.
SCR-044 | Global Search | Platform | /search | Supported/Partial | Cross-module results, filters, recent/saved search | Permission-scoped result adapters | Implement full search UX | Per-source permissions | Search audit optional | All modules | Wave 2 | P1 | Implement | Search must scope before retrieval; never fetch all then hide unauthorized records.
SCR-045 | Notification Center | Platform | /notifications | Partial | Unread, mentions, system updates, archive, preferences, deep links | Notification/Recipient/Preference models | Implement center/detail panel | Visibility by event + source permissions | Read/archive/delivery audit as needed | Email delivery | Wave 2 | P0 | Implement | Internal route_name/resource_id only; no arbitrary trusted URLs.
SCR-046 | Personal Preferences | Self-Service | /preferences | Partial | Locale, timezone, formats, theme, density, accessibility, notifications | Preference persistence | Implement page | user.manage_own_preferences | Preference audit optional | User profile | Wave 2 | P1 | Implement | Formatting preference never silently converts accounting currencies.
SCR-047 | Security Center | Self-Service | /security | Partial | Password, TOTP, email OTP, sessions, security activity, recovery email | UserSession + email OTP + recovery email | Implement security page | user.manage_own_security | Mandatory security audit | Auth/BFF + email | Wave 2 | P0 | Implement | SMS/recovery phone hidden until reliable SMS provider exists.
SCR-048 | Roles & Permissions | Settings | /settings/roles | Supported/Partial | System vs custom roles; matrix; review changes | Permission aggregation + secure update contract | Implement role editor | role.manage | All permission changes audited | RBAC | Wave 2 | P0 | Implement | UI View/Create/Manage/Approve maps to granular backend permissions.
SCR-049 | Users & Access | Users & Access | /users-access | Supported/Partial | Members, invitations, access requests, activity | AccessRequest model; invite enhancements | Implement tabs/list | membership.manage | Membership/invite/access audited | RBAC + approvals | Wave 2 | P0 | Implement | Invitation links one-time/expiring; access requests use governed approval.
SCR-050 | Module Management | Settings | /settings/modules | Supported | Dependencies, enable/disable, configure | Dependency validation if incomplete | Implement settings surface | module.manage | Module changes audited | InstitutionModule | Wave 2 | P1 | Implement | Keep activation/dependencies; defer SaaS billing-plan mechanics unless productized.
SCR-051 | Institution Profile | Settings | /settings/institution | Supported/Partial | Logo, currency, timezone, contact/address | Institution fields + logo storage | Implement page | institution.manage | Changes audited | Institution | Wave 2 | P1 | Implement | Country may suggest currency but never silently overwrite manual choice.
SCR-052 | Confirmation Dialog patterns | Design System | shared | Partial | Governed confirmation variants for approve/discard/deactivate/delete | None/minimal | Create reusable component family | Action-specific | Action audit occurs in domain | Design System | Wave 1 | P0 | Implement | Destructive actions clearly distinguish reversible vs permanent.
SCR-053 | Empty/Error/Loading states | Design System | shared | Partial | Reusable no-data, no-access, error, loading, zero-results patterns | Standard error contract helpful | Implement primitives | Permission-aware | No extra audit | Design System | Wave 1 | P0 | Implement | No production placeholder/demo data.
SCR-054 | Mobile/PWA navigation | PWA | shared responsive shell | PWA supported | Drawer + bottom nav + compact employee workspace | Minimal | Implement responsive shell | Same permission/module rules | None | PWA | Wave 1 | P1 | Implement | No sensitive API/tenant data cached offline.

## Feature Backlog
Feature ID | Capability | Domain | Description | New Models / Services | Primary Dependencies | Priority | Wave | Status | Key Rule / Guardrail
FEAT-001 | Governed Record Pattern | Platform | Shared lifecycle conventions for sensitive records; domain-specific transitions. | Shared transition contract; lineage metadata; reusable UI primitives | Audit + approvals | P0 | Wave 0/1 | Approved | Finalized/posted records corrected by linked correction/reversal rather than destructive edit.
FEAT-002 | Approval Workflow Engine | Platform | Institution-configurable stage sequences for supported trigger types. | ApprovalWorkflow, Stage, Request, Step, Decision, Delegation, Escalation | RBAC + notifications | P0 | Wave 0/2 | Approved | Start with supported approver types; do not build arbitrary no-code automation engine.
FEAT-003 | Email OTP MFA | Security | Email-delivered OTP as second factor alongside TOTP. | EmailOTPChallenge service | Email provider + rate limiting | P0 | Wave 2 | Approved | Hash OTP; expiry; single use; resend cooldown; attempt limits; audit.
FEAT-004 | Session Management | Security | List/revoke active authenticated sessions. | UserSession/session-family tracking | BFF auth | P0 | Wave 2 | Approved | Revocation must invalidate authorization, not only UI state.
FEAT-005 | Notification Center | Platform | In-app notification inbox with deep-linked governed records. | Notification, NotificationRecipient, NotificationPreference | Email + source modules | P0 | Wave 2 | Approved | Use internal route_name/resource_id; source authorization rechecked on open.
FEAT-006 | Access Requests | Users & Access | Users request role/permission access routed through approval. | AccessRequest | Approval engine + RBAC | P1 | Wave 2 | Approved | Changes applied only after authorized approval and audited.
FEAT-007 | Job Requisitions | Recruitment | Pre-posting hiring request with business justification, headcount and approvals. | JobRequisition, RequisitionTeamMember | Approval engine + org structure | P1 | Wave 4 | Approved | Approved requisition can create/publish JobPosting.
FEAT-008 | Candidate Scorecards | Recruitment | Configurable evaluation criteria and reviewer submissions. | EvaluationTemplate, Criterion, Evaluation, Score | Recruitment | P1 | Wave 4 | Approved | Criteria configurable; no university-specific hardcoding.
FEAT-009 | Interview Management | Recruitment | Panel scheduling, timezone, agenda, invitation and interview status. | Interview enhancements | Notifications + email | P1 | Wave 4 | Approved | External calendar/Teams availability later.
FEAT-010 | Offer Lifecycle | Recruitment | Governed offer drafting, approval, sending, response and hire conversion. | Offer enhancements + response history | Approvals + docs | P1 | Wave 4 | Approved | Accepted offer conversion preserves recruitment lineage.
FEAT-011 | Attendance Adjustments | Attendance | Employee correction request with evidence, policy checks and review workflow. | AttendanceAdjustment, Evidence, validation service | Leave + schedules + approvals | P1 | Wave 3 | Approved | Cannot silently rewrite attendance already consumed by finalized payroll.
FEAT-012 | Leave Policy Evaluation | Leave | Policy engine returning PASS/FAIL/WARNING/NOT_EVALUATED. | Policy evaluation service | Leave types/policies | P1 | Wave 3 | Approved | Unavailable configuration never shown as compliant.
FEAT-013 | Payroll Validation & Exceptions | Payroll | Structured pre-approval validation with blocking exceptions. | PayrollValidationRule, PayrollException | Payroll engine + Ghana preset | P0 | Wave 5 | Approved | Blocking exceptions prevent progression.
FEAT-014 | Expense Management 2.0 | Accounting | Employee claims, receipts, policy validation, approval, finance review, GL posting and settlement. | ExpenseClaim, ExpenseItem, ExpenseAttachment, ExpensePolicy, mapping enhancements | Approvals + GL + documents | P0 | Wave 6 | Approved | No hard delete after approval/posting; journal mapping configurable.
FEAT-015 | Bank Reconciliation | Accounting | Imported statements, transaction matching, unmatched items and session completion. | BankStatement, Line, ReconciliationSession, Match | BankAccount + GL | P1 | Wave 7 | Approved | Start with imported/manual matching; bank feeds later.
FEAT-016 | Budgeting | Accounting | Department/account budgets with allocated, actual, remaining and variance. | Budget, BudgetLine, BudgetPeriod, BudgetRevision | GL dimensions | P2 | Wave 7 | Approved for Phase 2 | Do not show committed amounts until valid commitment source exists.
FEAT-017 | Reporting Catalogue | Reports | Catalog dashboards/reports with ownership, freshness, access and saved configurations. | ReportDefinition/metadata, sharing model | Reporting APIs | P2 | Wave 8 | Approved staged | Do not attempt generic BI builder first.
FEAT-018 | Global Search 2.0 | Platform | Institution-scoped permission-aware cross-module search. | Search adapters/index contract | All modules + RBAC | P1 | Wave 2 | Approved | Scope authorization before result retrieval.
FEAT-019 | Personal Preferences | Platform | Locale, timezone, theme, accessibility and notification choices. | Preference store | User account | P1 | Wave 2 | Approved | Formatting preferences never change transaction currency.
FEAT-020 | Responsive PWA Shell | Frontend/PWA | Desktop, tablet and mobile navigation aligned to concepts. | Frontend only mostly | Existing PWA | P1 | Wave 1 | Approved | No API/tenant/JWT offline caching; no offline writes.

## Roles & Routing
Role / User Type | Default Landing | Executive Dashboard | Insights | Employee Home | Notes / Rule
Platform Super Admin | Platform admin surface | No tenant executive landing by default | As explicitly permitted | No | Separate from tenant RBAC.
Institution Admin | Executive Dashboard | Yes | Optional/secondary | Optional if also Employee | Primary executive/administrative landing.
Director / CEO / Director-General | Executive Dashboard | Yes | Optional/secondary | Optional if also Employee | Equivalent executive title resolved through role/permission mapping.
HR Admin / HR Officer | Insights | No unless explicitly granted executive permission | Yes | Optional if Employee | Insights limited to permitted HR/workforce data.
Finance Manager / Accountant | Insights | No unless explicitly granted executive permission | Yes | Optional if Employee | Insights limited to permitted finance/payroll/accounting data.
Recruitment Officer | Insights | No | Yes | Optional if Employee | Recruitment-focused insights.
Payroll Officer | Insights | No | Yes | Optional if Employee | Payroll-focused insights.
Auditor | Insights or Audit Trail | No unless explicitly granted | Yes, read-only scope | No | Read-only analytical/audit access.
Department Manager | Insights | No | Yes | Optional if Employee | Department-scoped where applicable.
Standard Employee | Employee Home | No | No by default | Yes | Self-service landing. Analytics only if separately granted.
Custom Role | Permission resolved | Only with dashboard.executive.view | With analytics.insights.view | If employee self-service perms | Never route solely from display role title.

## Expense Design
Expense Management 2.0 — Phase 2 Design
Area | Phase 2 Design | Core Fields / Components | Key Permission | Audit Requirement | Accounting Impact | Priority | Guardrail
Lifecycle | Draft → Submitted → Manager Approval → Finance Review → Approved → Posted → Settled | status, submitted_at, approved_at, posted_at, settled_at | expense.* | All transitions | Creates configured GL entries | P0 | Posted/settled claims cannot be hard-deleted.
ExpenseClaim | Header-level employee expense request | institution, employee, claim_number, purpose, business_reason, currency, total_amount | expense.create_own / expense.view_* | Create/update/submit | Header for posting | P0 | Institution scoped.
ExpenseItem | Individual claim line | date, category, merchant, description, amount, tax, project, department, cost centre | expense.edit_own_draft | Line changes | Maps to expense/tax accounts | P0 | No silent account inference.
ExpenseAttachment | Receipt/invoice/evidence | file, type, uploaded_by, uploaded_at | expense.attach | Upload/download | Evidence only | P0 | Malware/file validation and access controls.
ExpenseCategory | Institution-configurable category | name, code, active, receipt rules, limits | expense.configure_categories | Config changes | Maps to GL expense account | P1 | Deactivate when referenced; do not delete.
ExpensePolicy | Validation rules | receipt threshold, category cap, daily cap, allowed currency, required evidence | expense.configure_policy | Config changes | May block approval/posting | P1 | Rules must be explicit and institution-configured.
Manager Review | Approve/decline/request changes | comments, decision, delegation | expense.approve_manager | Mandatory | No posting yet | P0 | Decision authority comes from approval workflow.
Finance Review | Validate coding and completeness | account mapping, tax treatment, settlement method | expense.finance_review | Mandatory | Prepares posting | P0 | Finance cannot bypass unresolved blocking exceptions.
Posting | Generate balanced journal | debit expense/tax; credit employee payable or configured liability | expense.post | Mandatory | Creates immutable posted journal | P0 | Must use institution mappings.
Settlement | Record reimbursement/payment | settlement date, reference, amount, method | expense.settle | Mandatory | Dr payable / Cr bank-cash or configured settlement | P1 | Marking settled ≠ bank transfer unless integration exists.
Self-Service | My Expenses | draft/submitted/pending/approved/rejected/awaiting reimbursement/reimbursed | expense.view_own | View/download | None directly | P1 | Employees see only own claims.
Validation | Pre-submit/pre-post checks | missing receipt, duplicate receipt, invalid date, inactive claimant, unsupported currency, closed period, missing mapping | system + reviewers | Validation events | May block posting | P0 | Classify checks as warning vs blocking.

## Wave Plan
Wave | Name | Scope | Entry Criteria | Exit Criteria | Risk Level | Dependencies
Wave 0 | Contracts & Governance | Concept register, route/API/permission inventory, governed-record standard, approval/notification architecture | Phase 2 scope approved | Authoritative implementation contracts frozen | High | Current backend/domain review
Wave 1 | Design System v2 & Shell | Tokens, primitives, shell, responsive navigation, states, dialogs, accessibility | Wave 0 architecture decisions | Golden screen passes desktop/tablet/mobile visual QA | Medium | Stitch final designs
Wave 2 | Platform Capabilities | Notifications, global search, preferences, sessions/security, RBAC UI, Users & Access, module settings | Design system stable | Core platform services integrated and audited | High | Auth/RBAC/email
Wave 3 | HR & Self-Service | Home, Executive, Insights, employees, leave, attendance, My Workspace | Platform capabilities ready | Role routing and workforce workflows pass E2E tests | High | HR/Leave/Attendance APIs
Wave 4 | Recruitment 2.0 | Requisitions, hiring teams, evaluations, interviews, offers, lineage | Approval engine ready | Requisition→hire→employee path validated | High | Recruitment + approvals
Wave 5 | Payroll 2.0 | Validation rules, exceptions, approvals, lifecycle, Ghana preset integration | Governed records + approvals ready | Blocking exceptions and payroll lifecycle validated | Very High | Payroll/Ghana preset
Wave 6 | Accounting 2.0 | GL, AP, AR, Expenses, accounting documents, approval/audit integration | Payroll contracts stable | Finance workflows balanced, permissioned and auditable | Very High | GL mappings + approvals
Wave 7 | Finance Expansion | Bank reconciliation, budgeting, advanced financial reports | Accounting 2.0 stable | Reconciliation and budget/report integrity tests pass | High | GL dimensions
Wave 8 | Advanced Enterprise | Report catalogue/scheduling, public careers, external calendar/bank integrations, broader automation | Core Phase 2 stable | Selected integrations released behind explicit controls | High | External providers

## Decision Log
Decision ID | Decision | Rationale | Implication | Status
DEC-001 | MFA = TOTP + email OTP; no SMS for now | No reliable SMS provider | Hide SMS/recovery-phone verification; implement secure email OTP | Locked
DEC-002 | Executive Dashboard audience = Institution Admin + Director/CEO equivalents | Strategic institution-wide oversight | Use executive dashboard permission and module-aware aggregation | Locked
DEC-003 | Insights audience = other authorized operational/admin roles | Separates strategic and operational analytics | Permission-filtered Insights; Employee lands on self-service | Locked
DEC-004 | Expenses remains a current Accounting capability and expands in Phase 2 | Expense workflow is already part of product scope | Implement Expense Management 2.0 with approval, GL and settlement controls | Locked
DEC-005 | Phase 2 has begun | Concept work now drives controlled implementation expansion | Functional backend extensions allowed after register review | Locked
DEC-006 | Stitch is visual authority; backend/domain rules are functional authority | Prevents concept art from redefining business invariants | No direct 'copy screen = implement feature' behavior | Locked
DEC-007 | Procurement, Learning, Performance, Benefits are not silently added from concept navigation | Concepts include future-scope examples | Only add through explicit future scope approval | Locked
DEC-008 | No production placeholder/demo data | Credibility and data integrity | Use governed empty/loading/error states | Locked

## Dashboard Governance
Surface | Audience | Allowed Metric Examples | Conditional Rules | Do Not Show / Guardrail
Executive Dashboard | Institution Admin; Director/CEO/equivalent | Total employees, active workforce, payroll cost, revenue, workforce trend, receivables, compliance/posting health | Only metrics from enabled modules and authorized institution scope | No invented productivity/performance scores; no accounting metrics if Accounting disabled.
Insights | Other authorized admin/operational roles | Role-relevant HR, recruitment, leave, attendance, payroll, accounting insights | Filter by permissions, module enablement, department/institution scope | Do not expose data solely because user can open Insights.
HR Dashboard | HR roles | Headcount, hires, turnover, department counts, onboarding issues, leave/attendance queues | Use HR permissions and date range | No executive finance metrics.
Employee Home | Standard Employee | Today's attendance, next shift, leave balance, latest payslip, personal documents/activity | Only own records; module-aware | No coworker rankings or organization-wide data.
Self-Service Dashboard | Standard Employee | Attendance trend, leave usage, next pay date, recent payslips, milestones | Only own records and supported calculations | No inferred performance/productivity scoring.
Accounting Dashboard | Finance roles | Unposted journals, approvals, reconciliation exceptions, close status, cash flow | Only if corresponding accounting capability exists | Do not present close status if no period-close model exists.

## Summary
Phase 2 Register Summary
Metric | Count
Concept screens registered | 54
P0 screens | 9
P1 screens | 38
P2 screens | 7
Feature backlog items | 20
Implementation waves | 9