## README
ErgonX Phase 2 — Wave 0 Technical Contract Pack
Authority order: Backend/domain invariants → this contract pack → approved design system/Stitch screens → implementation. This workbook is a planning contract based on the approved ErgonX architecture and Phase 2 decisions; items marked VERIFY require codebase/API confirmation before implementation.
Contract Area | Purpose | Key Rule | Status | Owner | Gate | Notes
Route Inventory | Prevent duplicate/conflicting routes and normalize navigation. | One canonical route per screen/surface; redirects allowed, duplicate business pages are not. | Draft contract | Frontend/Platform | Wave 0 | Routes marked NEW require backend capability and permission contract before UI is wired.
API Inventory | Separate existing backend support from required Phase 2 APIs. | Frontend must not invent fields/endpoints; backend contract is authoritative. | Draft contract | Backend/API | Wave 0 | VERIFY entries need code inspection/OpenAPI confirmation.
Permission Matrix | Ensure access decisions are permission-driven, not display-role driven. | Role names seed permissions; backend permissions authorize actions. | Draft contract | Security/RBAC | Wave 0 | Platform Super Admin remains separate from tenant RBAC.
Lifecycle Matrix | Define legal state transitions for governed records. | Finalized/posted records are corrected through linked correction/reversal flows. | Draft contract | Domain/Backend | Wave 0 | Each module owns its exact state machine; shared pattern supplies conventions.
Discrepancy Actions | Turn known limitations/gaps into explicit Phase 2 actions. | Do not erase historical discrepancies; superseded items stay traceable. | Draft contract | All | Wave 0 | Current known P0 remains none; Phase 2 introduces deliberate new scope.
Routing Rule | Define landing surfaces by effective access. | Institution Admin/Director/CEO → Executive Dashboard; other authorized operational roles → Insights; standard Employee → Employee Home. | Locked | Platform | Wave 0 | Use permissions/effective institutional role, not literal title matching only.
MFA Rule | Define supported factors for Phase 2. | TOTP + email OTP only; no SMS OTP until reliable provider exists. | Locked | Security | Wave 2 | Recovery phone UI remains hidden until SMS verification exists.
Expenses Rule | Treat Expenses as active Accounting capability. | Employee claim → approval → finance review → GL posting → settlement. | Locked | Accounting | Wave 6 | No hard delete after approval/posting; mappings configured, never inferred by hard-coded account IDs.

## Route Inventory
Route Inventory
Canonical proposed route map for Phase 2. 'VERIFY' means confirm exact existing path before changing the codebase.
ID | Surface | Canonical Route | Current / Existing Route | Contract Status | Module | Required Access | Landing Eligible | Phase 2 Wave | Implementation Notes
RT-001 | Login | /login | /login | KEEP | AUTH | Public | No | Wave 1 | Single login portal; no role-specific login pages.
RT-002 | Institution Registration | /register | VERIFY | EXTEND | ONBOARDING | Public create-organization flow | No | Wave 3 | Creates institution + first admin + onboarding state.
RT-003 | Home Workspace | /home | /home | KEEP | HOME | Authenticated + source permissions | Conditional | Wave 3 | Daily workspace, not Executive Dashboard.
RT-004 | Executive Dashboard | /executive | VERIFY | EXTEND | REPORTS | dashboard.executive.view | Yes: Institution Admin/Director/CEO | Wave 3 | Module-aware institution-wide strategic dashboard.
RT-005 | Insights | /insights | VERIFY | EXTEND | REPORTS | analytics.insights.view | Yes: other operational/admin roles | Wave 3 | Permission-filtered analytics surface.
RT-006 | HR Dashboard | /hr/dashboard | VERIFY | KEEP/REFINE | CORE_HR | hr.dashboard.view | No | Wave 3 | Role-specific operational dashboard.
RT-007 | Employees | /employees | VERIFY | KEEP/REFINE | CORE_HR | employee.view | No | Wave 3 | Employee list + side preview.
RT-008 | Employee Detail | /employees/:employeeId | VERIFY | KEEP/REFINE | CORE_HR | employee.view | No | Wave 3 | Tabs for employment, compensation, attendance/leave, payroll, docs, history.
RT-009 | Recruitment | /recruitment | VERIFY | KEEP/REFINE | RECRUITMENT | recruitment.view | No | Wave 4 | Recruitment pipeline.
RT-010 | Job Requisition Create | /recruitment/requisitions/new | NEW | NEW | RECRUITMENT | requisition.create | No | Wave 4 | Phase 2 domain addition.
RT-011 | Job Requisition Detail | /recruitment/requisitions/:requisitionId | NEW | NEW | RECRUITMENT | requisition.view | No | Wave 4 | Approval/publish lifecycle.
RT-012 | Candidate Detail | /recruitment/candidates/:candidateId | VERIFY | KEEP/EXTEND | RECRUITMENT | candidate.view | No | Wave 4 | Evaluation/scorecard, docs, interviews, activity.
RT-013 | Interview Schedule | /recruitment/interviews/new | VERIFY | EXTEND | RECRUITMENT | interview.manage | No | Wave 4 | Base scheduler first; no fake external calendar availability.
RT-014 | Offer Detail | /recruitment/offers/:offerId | VERIFY | KEEP/EXTEND | RECRUITMENT | offer.view | No | Wave 4 | Approval, send, response, conversion.
RT-015 | Leave Dashboard | /leave | VERIFY | KEEP/REFINE | LEAVE | leave.view | No | Wave 3 | Admin/manager operational surface.
RT-016 | Leave Request Review | /leave/requests/:requestId/review | VERIFY | EXTEND | LEAVE | leave.approve | No | Wave 3 | Team availability + policy + docs + history.
RT-017 | Attendance Dashboard | /attendance | VERIFY | KEEP/REFINE | ATTENDANCE | attendance.view | No | Wave 3 | Exceptions + adjustment queue.
RT-018 | Attendance Adjustment Review | /attendance/adjustments/:adjustmentId | NEW/VERIFY | NEW/EXTEND | ATTENDANCE | attendance.adjustment.review | No | Wave 3 | Evidence and governed correction flow.
RT-019 | Payroll Workspace | /payroll | VERIFY | KEEP/REFINE | PAYROLL | payroll.view | No | Wave 5 | Current run, compliance, approvals, employee breakdown.
RT-020 | Payroll Run Detail | /payroll/runs/:runId | VERIFY | KEEP/EXTEND | PAYROLL | payroll.view_run | No | Wave 5 | Exceptions/approvals/activity tabs.
RT-021 | Accounting Dashboard | /accounting | VERIFY | KEEP/REFINE | ACCOUNTING | accounting.dashboard.view | No | Wave 6 | Finance health dashboard.
RT-022 | General Ledger | /accounting/general-ledger | VERIFY | KEEP/REFINE | ACCOUNTING | gl.view | No | Wave 6 | COA + journals + account detail.
RT-023 | Journal Detail | /accounting/journals/:journalId | VERIFY | KEEP/EXTEND | ACCOUNTING | journal.view | No | Wave 6 | Lines, related records, attachments, approvals, audit.
RT-024 | Accounts Payable | /accounting/ap | VERIFY | KEEP/REFINE | ACCOUNTING | ap.view | No | Wave 6 | Bills, vendors, payment/approval workflow.
RT-025 | Vendor Bill Detail | /accounting/ap/bills/:billId | VERIFY | KEEP/EXTEND | ACCOUNTING | ap.bill.view | No | Wave 6 | Document + approval + payment state.
RT-026 | Accounts Receivable | /accounting/ar | VERIFY | KEEP/REFINE | ACCOUNTING | ar.view | No | Wave 6 | Invoices, aging, receipts, collections controls.
RT-027 | Customer Invoice Detail | /accounting/ar/invoices/:invoiceId | VERIFY | KEEP/EXTEND | ACCOUNTING | ar.invoice.view | No | Wave 6 | Payment history, credits/voids, reminders.
RT-028 | Expenses Admin | /accounting/expenses | VERIFY | KEEP/EXTEND | ACCOUNTING | expense.view_all / expense.finance_review | No | Wave 6 | Accounting submodule.
RT-029 | My Expenses | /my-workspace/expenses | NEW | NEW | ACCOUNTING | expense.view_own | No | Wave 6 | Employee-facing claim lifecycle.
RT-030 | Bank Reconciliation | /accounting/bank-reconciliation | NEW/VERIFY | NEW/EXTEND | ACCOUNTING | bank.reconcile | No | Wave 7 | Imported/manual reconciliation first.
RT-031 | Reconciliation Session | /accounting/bank-reconciliation/:sessionId | NEW | NEW | ACCOUNTING | bank.reconcile | No | Wave 7 | Match/unmatch session detail.
RT-032 | Budgets | /accounting/budgets | NEW/VERIFY | NEW | ACCOUNTING | budget.view | No | Wave 7 | Phase 2 finance expansion.
RT-033 | Financial Reports | /accounting/financial-reports | VERIFY | KEEP/EXTEND | ACCOUNTING | financial_report.view | No | Wave 7 | Formal accounting statements.
RT-034 | Reports & Analytics | /reports | VERIFY | KEEP/EXTEND | REPORTS | report.view | No | Wave 8 | Report/dashboard catalogue, saved configs, sharing later.
RT-035 | Approvals | /approvals | VERIFY | KEEP/EXTEND | PLATFORM | approval.inbox.view | No | Wave 2 | Cross-module approval inbox.
RT-036 | Audit Trail | /audit | VERIFY | KEEP/REFINE | PLATFORM | audit.view | No | Wave 2 | Standalone module.
RT-037 | Users & Access | /users-access | VERIFY | KEEP/EXTEND | PLATFORM | membership.manage | No | Wave 2 | Members, invitations, access requests.
RT-038 | Settings | /settings | VERIFY | KEEP/REFINE | PLATFORM | settings.view | No | Wave 2 | Canonical settings shell.
RT-039 | Roles & Permissions | /settings/roles | VERIFY | KEEP/EXTEND | PLATFORM | role.manage | No | Wave 2 | System/custom role editor.
RT-040 | Modules | /settings/modules | VERIFY | KEEP/REFINE | PLATFORM | module.manage | No | Wave 2 | Module dependency-aware settings.
RT-041 | Institution Profile | /settings/institution | VERIFY | KEEP/REFINE | PLATFORM | institution.manage | No | Wave 2 | Branding, currency, timezone, contact.
RT-042 | Approval Workflows | /settings/approval-workflows | VERIFY | EXTEND | PLATFORM | approval.workflow.manage | No | Wave 2 | Configurable supported workflow stages.
RT-043 | Notifications | /notifications | VERIFY | EXTEND | PLATFORM | notification.view_own | No | Wave 2 | In-app center with governed deep links.
RT-044 | Global Search | /search | VERIFY | KEEP/EXTEND | PLATFORM | search.use | No | Wave 2 | Permission-scoped search.
RT-045 | Personal Preferences | /preferences | VERIFY | EXTEND | SELF_SERVICE | user.manage_own_preferences | No | Wave 2 | Locale, theme, accessibility, notification preferences.
RT-046 | Security Center | /security | VERIFY | EXTEND | SELF_SERVICE | user.manage_own_security | No | Wave 2 | Password, TOTP, email OTP, sessions, security activity.
RT-047 | Employee Home | /my-workspace | VERIFY | KEEP/REFINE | SELF_SERVICE | self_service.home | Yes: Standard Employee | Wave 3 | Daily self-service landing.
RT-048 | Self-Service Dashboard | /my-workspace/dashboard | VERIFY | KEEP/REFINE | SELF_SERVICE | self_service.dashboard.view | No | Wave 3 | Personal analytics.
RT-049 | My Profile | /my-workspace/profile | VERIFY | KEEP/REFINE | SELF_SERVICE | profile.view_own | No | Wave 3 | Personal/employment/payment/tax sections.
RT-050 | My Documents | /my-workspace/documents | VERIFY | KEEP/REFINE | SELF_SERVICE | document.view_own | No | Wave 3 | Upload/search/category/expiry.
RT-051 | My Leave | /my-workspace/leave | VERIFY | KEEP/REFINE | SELF_SERVICE | leave.view_own | No | Wave 3 | Balances, requests, calendar.
RT-052 | Request Leave | /my-workspace/leave/request | VERIFY | KEEP/EXTEND | SELF_SERVICE | leave.create_own | No | Wave 3 | Draft, half-day, attachments, route preview.
RT-053 | My Attendance | /my-workspace/attendance | VERIFY | KEEP/EXTEND | SELF_SERVICE | attendance.view_own | No | Wave 3 | Calendar, daily records, adjustment request.
RT-054 | My Payslips | /my-workspace/payslips | VERIFY | KEEP/REFINE | SELF_SERVICE | payslip.view_own | No | Wave 3 | Secure finalized payslips only.

## API Inventory
API Inventory
Contract-level API inventory. Paths are proposed where Phase 2 APIs are new; confirm existing exact endpoints from current OpenAPI before coding.
ID | Capability | Proposed / Existing Endpoint | Method | Contract Status | Module | Request Contract | Response Contract | Authorization | Audit | Wave | Notes
API-001 | Resolve current session/context | /api/v1/me/context/ | GET | VERIFY/EXTEND | PLATFORM | Cookie/BFF auth + X-Institution-ID selector | User, memberships, active institution, role, permissions, modules, onboarding readiness | Authenticated; institution membership authoritative | Security context access optional | Wave 2 | X-Institution-ID selects context; never grants access.
API-002 | Executive dashboard summary | /api/v1/dashboards/executive/ | GET | NEW/EXTEND | REPORTS | period, location, optional institution if platform context | Module-aware KPI/series blocks | dashboard.executive.view + source data permissions | Read audit optional | Wave 3 | Exclude disabled modules rather than returning fake zeroes.
API-003 | Insights summary | /api/v1/insights/ | GET | NEW/EXTEND | REPORTS | period, department/location filters | Permission-filtered metric cards/series | analytics.insights.view + source perms | Read audit optional | Wave 3 | Role display name must not be authorization input.
API-004 | Global search | /api/v1/search/ | GET | VERIFY/EXTEND | PLATFORM | q, module, record_type, date/location/department filters | Grouped ranked results with safe route metadata | search.use + per-result source permissions | Optional search audit | Wave 2 | Authorize before retrieval.
API-005 | Notifications list | /api/v1/notifications/ | GET | VERIFY/EXTEND | PLATFORM | filters: unread, module, type | Recipient-scoped notifications | notification.view_own | No special audit | Wave 2 | No arbitrary URL payloads.
API-006 | Notification mark read/archive | /api/v1/notifications/:id/ | PATCH | NEW/EXTEND | PLATFORM | read/archive flags | Updated recipient state | notification.manage_own | State change event optional | Wave 2 | Recipient scoped.
API-007 | Notification preferences | /api/v1/notification-preferences/ | GET/PATCH | NEW | PLATFORM | in-app/email categories | Preference object | user.manage_own_preferences | Optional | Wave 2 | SMS channel omitted.
API-008 | Email OTP challenge create | /api/v1/auth/email-otp/challenge/ | POST | NEW | SECURITY | purpose | challenge_id, masked destination, expiry metadata | Authenticated or login challenge context | Mandatory security audit | Wave 2 | Store only hash of OTP.
API-009 | Email OTP verify | /api/v1/auth/email-otp/verify/ | POST | NEW | SECURITY | challenge_id, otp | verified / auth continuation | Challenge scoped | Mandatory security audit | Wave 2 | Rate-limit and consume once.
API-010 | Active sessions | /api/v1/security/sessions/ | GET | NEW | SECURITY | None | Device/browser/last_seen/current_session | user.manage_own_security | Security read optional | Wave 2 | Do not expose secrets/token material.
API-011 | Revoke session | /api/v1/security/sessions/:id/revoke/ | POST | NEW | SECURITY | None or confirmation | Revoked status | user.manage_own_security | Mandatory | Wave 2 | Must invalidate server-side authorization.
API-012 | Roles list/detail | /api/v1/access/roles/ | GET | VERIFY/EXTEND | RBAC | filters | System/custom roles + permission groups | role.view | Read optional | Wave 2 | Reserved system role codes protected.
API-013 | Role permission change review/apply | /api/v1/access/roles/:id/permissions/ | PATCH | VERIFY/EXTEND | RBAC | granular permission set or approved diff | Effective permission set | role.manage | Mandatory | Wave 2 | UI buckets View/Create/Manage/Approve map to granular permissions.
API-014 | Access requests | /api/v1/access/requests/ | GET/POST | NEW | RBAC | requested role/permission + reason | Request + approval state | membership/access request permissions | Mandatory | Wave 2 | Governed through Approval engine.
API-015 | Approval workflows | /api/v1/approval-workflows/ | GET/POST/PATCH | NEW/EXTEND | PLATFORM | module, trigger, ordered stages, escalation policy | Workflow definition | approval.workflow.manage | Mandatory | Wave 2 | Supported approver types only in first implementation.
API-016 | Approval inbox | /api/v1/approvals/ | GET | VERIFY/EXTEND | PLATFORM | status/module/assignee filters | Pending/completed requests | approval.inbox.view | Read optional | Wave 2 | Cross-module.
API-017 | Approval decision | /api/v1/approvals/:id/decision/ | POST | VERIFY/EXTEND | PLATFORM | approve/decline/request_changes/delegate + comment | Updated approval request | Approval step authority | Mandatory | Wave 2 | Backend validates stage authority.
API-018 | Job requisitions | /api/v1/recruitment/requisitions/ | GET/POST | NEW | RECRUITMENT | Role/hiring plan fields | Requisition record | requisition.view/create | Mandatory create/submit lifecycle audit | Wave 4 | New Phase 2 model.
API-019 | Requisition submit/publish | /api/v1/recruitment/requisitions/:id/submit/ ; /publish/ | POST | NEW | RECRUITMENT | Optional comments / confirmation | Lifecycle state | requisition.manage/approve/publish | Mandatory | Wave 4 | Publish only after approval if configured.
API-020 | Evaluation templates | /api/v1/recruitment/evaluation-templates/ | GET/POST/PATCH | NEW | RECRUITMENT | criteria, weights/labels if used | Template + criteria | recruitment.evaluation.configure | Mandatory config audit | Wave 4 | No hard-coded university criteria.
API-021 | Candidate evaluations | /api/v1/recruitment/applications/:id/evaluations/ | GET/POST | NEW/EXTEND | RECRUITMENT | criterion scores/comments | Per-evaluator submissions | candidate.evaluate | Mandatory | Wave 4 | Private evaluator notes permissioned.
API-022 | Interview schedule | /api/v1/recruitment/interviews/ | POST/PATCH | VERIFY/EXTEND | RECRUITMENT | datetime, timezone, duration, type, panel, location/link, agenda | Interview + notification state | interview.manage | Mandatory | Wave 4 | No live external availability until integrations exist.
API-023 | Offer lifecycle action | /api/v1/recruitment/offers/:id/action/ | POST | VERIFY/EXTEND | RECRUITMENT | submit_approval/send/record_response/convert_hire | Offer state + linked records | offer.manage + specific action perms | Mandatory | Wave 4 | Accepted offer preserves lineage to Employee.
API-024 | Leave policy evaluation | /api/v1/leave/requests/:id/policy-checks/ | GET | NEW/EXTEND | LEAVE | None | Checks with PASS/FAIL/WARNING/NOT_EVALUATED | leave.view/manage | Read optional | Wave 3 | Never collapse unknown into compliant.
API-025 | Leave review action | /api/v1/leave/requests/:id/review/ | POST | VERIFY/EXTEND | LEAVE | approve/decline/request_changes/delegate + comment | Updated request/approval state | leave.approve | Mandatory | Wave 3 | Supporting docs/policy requirements enforced.
API-026 | Attendance adjustments | /api/v1/attendance/adjustments/ | GET/POST | NEW/EXTEND | ATTENDANCE | work date, original/requested time, reason, evidence refs | Adjustment record | attendance.view_own/create_own or admin perms | Mandatory | Wave 3 | Institution/employee scoped.
API-027 | Attendance adjustment review | /api/v1/attendance/adjustments/:id/review/ | POST | NEW | ATTENDANCE | approve/decline/request_changes/delegate | Updated adjustment + effects | attendance.adjustment.review | Mandatory | Wave 3 | Finalized payroll dependency checked.
API-028 | Payroll run validation | /api/v1/payroll/runs/:id/validate/ | POST | NEW/EXTEND | PAYROLL | None/validation options | Validation result + exception summary | payroll.validate | Mandatory | Wave 5 | Ghana preset contributes configured validations only.
API-029 | Payroll exceptions | /api/v1/payroll/runs/:id/exceptions/ | GET | NEW | PAYROLL | filters by severity/status | Structured exceptions | payroll.view_run | Read optional | Wave 5 | Blocking flag authoritative.
API-030 | Resolve payroll exception | /api/v1/payroll/exceptions/:id/resolve/ | POST | NEW | PAYROLL | resolution type/note/reference | Resolved exception | payroll.resolve_exception | Mandatory | Wave 5 | Cannot bypass underlying data error where true fix is required.
API-031 | Expense claims | /api/v1/accounting/expenses/ | GET/POST | VERIFY/EXTEND | ACCOUNTING | claim header + items + attachments refs | ExpenseClaim detail | expense.create_own / expense.view_* | Mandatory lifecycle audit | Wave 6 | Institution scoped.
API-032 | Expense submit/review | /api/v1/accounting/expenses/:id/action/ | POST | NEW/EXTEND | ACCOUNTING | submit/approve/decline/request_changes/finance_review | Updated lifecycle | expense.* action perms | Mandatory | Wave 6 | Approval engine authoritative.
API-033 | Expense post | /api/v1/accounting/expenses/:id/post/ | POST | NEW/EXTEND | ACCOUNTING | Posting confirmation | Draft/posted journal linkage | expense.post | Mandatory | Wave 6 | Fail closed on unresolved account mappings/closed period.
API-034 | Expense settlement | /api/v1/accounting/expenses/:id/settle/ | POST | NEW/EXTEND | ACCOUNTING | date, amount, method, reference | Settlement record/status | expense.settle | Mandatory | Wave 6 | Settlement record ≠ external bank transfer.
API-035 | Bank statements | /api/v1/accounting/bank-statements/ | GET/POST | NEW | ACCOUNTING | bank_account + file/import data | Statement + parsed lines | bank.reconcile | Mandatory import audit | Wave 7 | CSV/import-based first.
API-036 | Reconciliation sessions | /api/v1/accounting/reconciliations/ | GET/POST | NEW | ACCOUNTING | bank account, statement period | Session summary | bank.reconcile | Mandatory | Wave 7 | Opening/closing balance and invariant checks.
API-037 | Reconciliation match/unmatch | /api/v1/accounting/reconciliations/:id/matches/ | POST/DELETE | NEW | ACCOUNTING | bank line + book entry | Match result | bank.reconcile | Mandatory | Wave 7 | All match state changes auditable.
API-038 | Budgets | /api/v1/accounting/budgets/ | GET/POST/PATCH | NEW | ACCOUNTING | period, dimensions, lines | Budget detail | budget.view/manage | Mandatory | Wave 7 | Actual comes from posted GL.
API-039 | Financial report run | /api/v1/accounting/financial-reports/:id/run/ | POST | VERIFY/EXTEND | ACCOUNTING | report parameters | Generated report metadata/data | financial_report.run | Mandatory generation audit | Wave 7 | Output formats limited to implemented exporters.

## Permission Matrix
Permission Matrix
Canonical permission intent for Phase 2. Role assignments are examples; backend granular permissions remain authoritative.
Permission / Capability | Institution Admin | Director/CEO | HR Admin | Finance Manager | Accountant | Recruitment Officer | Payroll Officer | Auditor | Employee | Rule / Notes
dashboard.executive.view | Y | Y | N | N | N | N | N | N | N | Executive strategic dashboard; custom roles may receive explicitly.
analytics.insights.view | Optional | Optional | Y | Y | Y | Y | Y | Y (read scope) | N | Operational analytics filtered by source permissions.
employee.view | Y | Y | Y | Scoped | Scoped | Scoped | Scoped | Read | Own only | Field-level access may further restrict compensation/payroll data.
employee.manage | Y | N/Optional | Y | N | N | N | N | N | Own profile subset | Admins cannot use admin HR powers to edit own protected HR record.
requisition.create/manage | Y | Optional | Y | N | N | Y | N | Read if granted | N | Requires RECRUITMENT module.
candidate.evaluate | Optional | Optional | Y | N | N | Y | N | Read if granted | N | Panel membership may further scope.
leave.approve | Y | Optional | Y | N | N | N | N | Read if granted | N | Manager/role/approval workflow determines authority.
attendance.adjustment.review | Y | Optional | Y | N | N | N | N | Read if granted | N | May be delegated through workflow.
payroll.view/manage | Y | Optional summary | Scoped HR side | Y | Y | N | Y | Read | Own payslip only | Sensitive payroll fields require explicit permissions.
payroll.resolve_exception | Y | N/Optional | Scoped | Y | Y | N | Y | Read | N | Resolution authority should match exception type and business responsibility.
journal.create/post | Y | N/Optional | N | Y | Y | N | N | Read | N | Segregation of duties may separate create/approve/post.
ap.view/manage | Y | Optional | N | Y | Y | N | N | Read | N | Accounting module required.
ar.view/manage | Y | Optional | N | Y | Y | N | N | Read | N | Accounting module required.
expense.create_own | Y if employee | Y if employee | Y if employee | Y if employee | Y if employee | Y if employee | Y if employee | N/Optional | Y | Self-service permission available to employees.
expense.approve_manager | Y | Optional | Manager dependent | Manager dependent | Manager dependent | Manager dependent | Manager dependent | N | N | Approval workflow resolves actual approver.
expense.finance_review/post | Y | N | N | Y | Y (if granted) | N | N | Read | N | Posting requires GL permission and mapping resolution.
bank.reconcile | Y | N/Optional | N | Y | Y | N | N | Read | N | Finance-only operational access.
budget.manage/approve | Y | Optional | N | Y | Y/Scoped | N | N | Read | N | Approval workflow may separate manage and approve.
approval.workflow.manage | Y | N | N/Optional | N/Optional | N | N | N | Read | N | Highly privileged institution configuration.
role.manage | Y | N | N | N | N | N | N | Read | N | System roles protected; custom roles configurable.
membership.manage | Y | N | N/Optional | N | N | N | N | Read | N | Invite/disable/access request decisions audited.
audit.view | Y | Optional | Scoped | Scoped | Scoped | Scoped | Scoped | Y | Own security activity only | Audit field visibility may be restricted.
user.manage_own_security | Y | Y | Y | Y | Y | Y | Y | Y | Y | Password, TOTP, email OTP, sessions.

## Lifecycle Matrix
Lifecycle / State Matrix
State machines below are Phase 2 contract targets. Exact existing model enum names should be reconciled rather than blindly renamed.
Domain Record | State | Allowed Next State(s) | Who Can Transition | Validation / Preconditions | Editable? | Hard Delete? | Correction Method | Audit Requirement
Employee | ACTIVE | INACTIVE / OFFBOARDED / ARCHIVED | Authorized HR/Admin | Cannot use admin power on own protected HR record | Yes, authorized fields | No if referenced | Lifecycle action / subsequent HR change | Mandatory
Employee | INACTIVE | ACTIVE / ARCHIVED | Authorized HR/Admin | Rehire/reactivation rules | Limited | No | Reactivation creates history event | Mandatory
Job Requisition | DRAFT | SUBMITTED | Creator/Recruitment | Required fields complete | Yes | Yes if unreferenced | Edit draft | Mandatory create/update
Job Requisition | SUBMITTED | APPROVED / REJECTED / CHANGES_REQUESTED | Approver | Approval workflow | No except governed change request | No | Return to draft or correction process | Mandatory
Job Requisition | APPROVED | OPEN / CLOSED | Authorized Recruiter | Approval complete | Limited | No | New revision or close | Mandatory
Application | DRAFT | SUBMITTED | Candidate/Recruiter | Required application fields | Yes | Yes if safe/unsubmitted | Edit draft | Mandatory
Application | SUBMITTED | SCREENING / WITHDRAWN | Recruitment | Submission valid | Limited | No | Correction record / linked history where needed | Mandatory
Application | SCREENING | INTERVIEW / REJECTED | Recruitment | Evaluation criteria as configured | Limited | No | Linked correction/history | Mandatory
Application | INTERVIEW | OFFER / REJECTED | Recruitment | Interview state complete as configured | Limited | No | Linked correction/history | Mandatory
Application | OFFER | HIRED / REJECTED / WITHDRAWN | Recruitment | Offer response | Limited | No | Linked correction/history | Mandatory
Application | HIRED | CONVERTED_TO_EMPLOYEE | System/Authorized HR | Employee conversion succeeds | Read-only | No | New linked Employee record | Mandatory lineage
Leave Request | DRAFT | SUBMITTED / CANCELLED | Employee/Authorized user | Required policy fields | Yes | Yes if unsubmitted/unreferenced | Edit draft | Mandatory
Leave Request | SUBMITTED | APPROVED / DECLINED / CHANGES_REQUESTED / CANCELLED | Approver/Employee where allowed | Policy checks + approvals | No except change flow | No | Request changes / new revision | Mandatory
Leave Request | APPROVED | COMPLETED / CANCELLED | System/Authorized HR | Date progression / cancellation rules | No | No | Correction/reversal if finalized history impacted | Mandatory
Attendance Adjustment | DRAFT | SUBMITTED | Employee/Authorized admin | Evidence/rationale if required | Yes | Yes if unsubmitted | Edit draft | Mandatory
Attendance Adjustment | SUBMITTED | APPROVED / DECLINED / CHANGES_REQUESTED | Reviewer | Schedule/leave/payroll dependency checks | No | No | New correction if later change needed | Mandatory
Attendance Adjustment | APPROVED | APPLIED | System/Authorized reviewer | No finalized-payroll conflict or governed downstream adjustment | No | No | Correction creates linked adjustment | Mandatory
Payroll Run | DRAFT | VALIDATING | Payroll authorized | Payroll data prepared | Yes | Only if safe/unreferenced | Edit draft | Mandatory
Payroll Run | VALIDATING | VALIDATION_FAILED / READY_FOR_APPROVAL | System | Run validation rules | No during execution | No | Fix source data / resolve exceptions | Mandatory
Payroll Run | VALIDATION_FAILED | DRAFT / VALIDATING | Payroll authorized | Blocking issues addressed | Limited | No | Resolve underlying issue | Mandatory
Payroll Run | READY_FOR_APPROVAL | APPROVAL_PENDING | Payroll authorized | No blocking exceptions | No | No | Return to draft only by governed action | Mandatory
Payroll Run | APPROVAL_PENDING | APPROVED / REJECTED | Approver | Approval workflow | No | No | Reject returns to controlled correction state | Mandatory
Payroll Run | APPROVED | FINALIZED | Authorized payroll/finance | Configuration complete | No | No | Reversal/adjustment only after finalization | Mandatory
Payroll Run | FINALIZED | PAID | Authorized payroll/finance | Payment recorded/confirmed | No | No | Linked adjustment/reversal | Mandatory
Payroll Run | PAID | — | — | Terminal operational state | No | No | Linked adjustment/reversal only | Mandatory
Journal | DRAFT | APPROVAL_PENDING / POSTED (if no approval required) | Finance | Balanced; open period; mappings resolved | Yes | Yes if unreferenced | Edit draft | Mandatory
Journal | APPROVAL_PENDING | APPROVED / REJECTED | Approver | Balanced and approval workflow | No | No | Reject to controlled correction/draft | Mandatory
Journal | APPROVED | POSTED | Authorized poster | Balanced; open period | No | No | Post | Mandatory
Journal | POSTED | — | — | Immutable | No | No | Reversing/correcting journal | Mandatory
Expense Claim | DRAFT | SUBMITTED / CANCELLED | Employee | Items valid; required receipts present | Yes | Yes if unsubmitted/unreferenced | Edit draft | Mandatory
Expense Claim | SUBMITTED | MANAGER_APPROVED / DECLINED / CHANGES_REQUESTED | Approver | Approval workflow | No | No | Request changes | Mandatory
Expense Claim | MANAGER_APPROVED | FINANCE_REVIEW | System/Finance | Manager approval complete | Limited finance coding only | No | Finance review | Mandatory
Expense Claim | FINANCE_REVIEW | APPROVED / CHANGES_REQUESTED / DECLINED | Finance | Mappings, policy, tax treatment, open period | Limited | No | Request changes | Mandatory
Expense Claim | APPROVED | POSTED | Finance poster | Balanced GL mappings resolved | No | No | Posting creates linked journal | Mandatory
Expense Claim | POSTED | SETTLED | Finance | Settlement recorded | No | No | Accounting reversal/adjustment if needed | Mandatory
Expense Claim | SETTLED | — | — | Terminal operational state | No | No | Linked correction/reversal only | Mandatory
Bank Reconciliation Session | DRAFT | IN_PROGRESS | Finance | Bank account + statement period selected | Yes | Yes if empty/unreferenced | Edit session | Mandatory
Bank Reconciliation Session | IN_PROGRESS | COMPLETED | Finance | Reconciliation invariants pass | Yes for matches | No | Reopen only via governed action if supported | Mandatory
Bank Reconciliation Session | COMPLETED | — | — | Locked unless governed reopening exists | No | No | Correction via new session/reopen policy | Mandatory

## Discrepancy Actions
Discrepancy → Phase 2 Action Register
Known limitations and concept-driven additions translated into Phase 2 actions. Historical register entries should remain preserved in the source discrepancy register.
ID | Discrepancy / Gap | Current Status | Phase 2 Decision | Required Action | Acceptance Evidence | Wave | Priority | Notes
D2-001 | HOME-001: not every create workflow uses shared references or emits UserActivityEvent | OPEN P1 | Resolve during platform/workflow consolidation | Standardize reference selection contracts and activity-event emission for designated business actions | E2E tests + audit/activity samples | Wave 2/3 | P1 | Do not force events for trivial read-only UI actions.
D2-002 | OPS-001: arbitrary typed imports/exports need explicit handlers | REVIEW P1 | Keep explicit typed-handler approach | Add handlers only for Phase 2 workflows that actually need import/export; no generic unsafe importer | Import/export tests per supported type | Wave 6/7 | P1 | Bank statement import is an explicit supported handler.
D2-003 | REPORT-001: CSV only; no XLSX/PDF | ACCEPTED_MVP P2 | Phase 2 staged enhancement | Do not expose unsupported export buttons; add formats only after backend exporters exist | Report export integration tests | Wave 7/8 | P2 | Financial report UI must match real exporters.
D2-004 | ERD-005: Accounts lack stable AccountTemplate/system_mapping provenance | OPEN P1 | Resolve before deeper accounting presets/reporting | Persist provenance/mapping metadata for instantiated accounts | Migration + mapping tests | Wave 6 | P0 | Needed for safer Ghana accounting preset evolution.
D2-005 | Ghana payroll: minimum wage basis unresolved | Documented limitation | Remain fail-closed/configuration-driven | Do not guess statutory interpretation; add explicit config/validation placeholder where legally verified values can be supplied | Validation tests + documentation | Wave 5 | P1 | No unsupported compliance claim.
D2-006 | Ghana payroll: pension eligibility/exemption gaps | Documented limitation | Phase 2 validation/config refinement | Represent eligibility/exemption configuration explicitly; fail closed where unresolved | Payroll scenario tests | Wave 5 | P1 | Version under Ghana preset.
D2-007 | Ghana payroll: mid-period proration gaps | Documented limitation | Phase 2 enhancement | Add configurable proration policy and effective-date handling | Proration unit tests | Wave 5 | P1 | Avoid hidden proration rules.
D2-008 | Ghana payroll: relief timing/validation gaps | Documented limitation | Phase 2 enhancement where verified | Model relief evidence/effective periods; validate configured data | Scenario tests | Wave 5 | P1 | No automatic legal certification.
D2-009 | Ghana payroll: overtime threshold legal validation unresolved | Documented limitation | Keep configurable + documented | Separate institutional overtime policy from statutory/localization rules | Validation tests | Wave 5 | P1 | Do not infer legal thresholds.
D2-010 | Email OTP MFA not yet part of current confirmed MFA implementation | NEW Phase 2 | Add; SMS remains excluded | Implement EmailOTPChallenge with hash/expiry/attempt/rate limits | Security tests + audit events | Wave 2 | P0 | TOTP remains supported.
D2-011 | Active session revocation not part of confirmed current security feature set | NEW Phase 2 | Add | Introduce server-tracked session/token family and revoke endpoints | Security E2E tests | Wave 2 | P0 | Revocation must invalidate actual auth.
D2-012 | Configurable approval workflow depth exceeds current simple approvals | NEW/EXTEND | Add controlled workflow engine | Supported trigger/stage/approver models, delegation/escalation | Workflow E2E tests | Wave 2 | P0 | Do not build arbitrary no-code automation engine.
D2-013 | JobRequisition was intentionally absent from MVP | Superseded MVP decision | Add in Phase 2 | Implement requisition→approval→posting lifecycle | Recruitment E2E | Wave 4 | P1 | Preserve existing JobPosting compatibility.
D2-014 | Candidate structured scorecards/evaluation templates are deeper than current model | NEW/EXTEND | Add | Evaluation template/criteria/submission models | Evaluation tests + RBAC | Wave 4 | P1 | Criteria configurable.
D2-015 | External calendar/Teams availability shown in concepts but not confirmed integration | Future integration | Defer provider integration | Implement internal scheduling first; clearly mark provider integration later | No fake availability in production | Wave 8 | P2 | Can store meeting links manually first.
D2-016 | Attendance adjustment evidence/policy/delegation workflow deeper than current attendance module | NEW/EXTEND | Add | AttendanceAdjustment + validation + approval integration | Adjustment E2E tests | Wave 3 | P1 | Check finalized payroll dependencies.
D2-017 | Payroll structured exception engine not yet confirmed at concept depth | NEW/EXTEND | Add | PayrollValidationRule + PayrollException and progression gates | Payroll validation suite | Wave 5 | P0 | Blocking exceptions stop progression.
D2-018 | Expenses exists, but concept requires deeper governed workflow | EXTEND | Implement Expense Management 2.0 | Claim/items/receipts/policy/approval/finance review/posting/settlement | Expense-to-GL E2E + audit | Wave 6 | P0 | No hard delete after approval/posting.
D2-019 | Manual/import-based bank reconciliation not yet confirmed at concept depth | NEW/EXTEND | Add in Phase 2 | Statement import, lines, sessions, matches, completion invariants | Reconciliation E2E tests | Wave 7 | P1 | Bank feeds later.
D2-020 | Budgeting concept introduces new accounting capability | NEW | Add after Accounting 2.0 stabilizes | Budget/lines/revisions, allocated/actual/variance | Budget-to-GL tests | Wave 7 | P2 | Do not show committed until commitment source exists.
D2-021 | Report catalogue/scheduling/sharing exceeds MVP reports | NEW/EXTEND | Stage in Phase 2 | Catalogue → saved configs → sharing → scheduling | Reporting tests per stage | Wave 8 | P2 | No generic BI builder initially.
D2-022 | Concepts contain Procurement/Learning/Performance/Benefits navigation examples | Future scope | Do not silently implement | Keep out of Phase 2 core unless separately approved | Navigation/feature flag review | Wave 8+ | P2 | Procurement remains future despite PO references.
D2-023 | Some concept screens show plan/subscription packaging | Future commercial layer | Defer | Keep module enablement/dependencies; omit billing-plan mechanics | Settings acceptance test | Wave 8+ | P2 | Do not imply monetization model not yet implemented.
D2-024 | Concept screens may show production-like sample data | Design artifact only | Prohibit placeholder/demo data in production | Use governed empty/loading/error states when data unavailable | UI acceptance tests | Wave 1 | P0 | Demo seed data only in explicit demo/test environments.

## Wave 0 Gates
Wave 0 Exit Gates
Do not begin high-risk functional implementation until these gates are satisfied. Low-risk Design System work may proceed in parallel.
Gate ID | Exit Condition | Evidence Required | Owner | Status | Failure / Blocker Rule
G0-01 | Canonical route map reconciled with actual frontend routes | Route diff showing KEEP/REDIRECT/NEW decisions | Frontend Lead | Not Started | Do not create duplicate business routes.
G0-02 | OpenAPI/API inventory reconciled with current backend | Current OpenAPI compared against API Inventory; VERIFY entries resolved | Backend Lead | Not Started | Frontend must not wire invented endpoint contracts.
G0-03 | Permission matrix reconciled with actual permission codes | Mapping document from UI actions to backend permissions | Security/Backend | Not Started | No role-name-only authorization.
G0-04 | Lifecycle matrices approved for Payroll, Journal, Expense, Leave, Attendance Adjustment, Recruitment | State diagrams + transition tests planned | Backend/Domain | Not Started | No implementation of irreversible actions without transition contract.
G0-05 | Approval engine boundary agreed | Supported triggers, approver types, delegation/escalation scope | Backend/Architecture | Not Started | Do not expand into arbitrary workflow automation.
G0-06 | Email OTP threat controls agreed | Expiry, resend cooldown, max attempts, throttling, audit, masking | Security | Not Started | No production email OTP without rate limiting and one-time consumption.
G0-07 | Expense-to-GL mappings contract agreed | Expense categories, mapping source, posting entries, closed-period behavior | Accounting/Backend | Not Started | No hard-coded account IDs or silent inference.
G0-08 | Ghana payroll localization gaps explicitly preserved | List of verified vs unresolved rules for GH-2026.1 | Payroll/Research | Not Started | No statutory values guessed to satisfy UI.
G0-09 | Stitch design references tagged to contract screens | Screen IDs mapped to final design frames | Design/Frontend | Not Started | Concept design cannot override domain invariants.
G0-10 | Test strategy defined for Wave 2–6 critical paths | Unit/integration/E2E/security test plan | QA/Engineering | Not Started | No high-risk module progression without test coverage plan.

## Summary
Wave 0 Summary
Inventory | Count | Priority | Discrepancy Actions
Routes registered | 54 | P0 | 7
API contracts registered | 39 | P1 | 11
Permission capabilities | 23 | P2 | 6
Lifecycle rows | 39
Discrepancy actions | 24
Wave 0 gates | 10