## README
ErgonX Phase 2 — Wave 0 Technical Contract Pack v2
Built against the normalized Stitch master pack ERGX-S001–ERGX-S066. This is the controlling pre-implementation contract for Codex; VERIFY items must be reconciled against the actual codebase/OpenAPI before coding.
Area | Contract Purpose | Authoritative Rule | Status | Wave | Primary Owner | Evidence | Notes
Screen Contract Map | Connect every Stitch concept to route, capability, wave and implementation decision. | No Stitch concept silently creates a new business capability. | Ready for reconciliation | Wave 0 | Product/Architecture | 66-screen map | Variants must merge into canonical implementations.
Canonical Routes | Prevent duplicate or competing business routes. | One canonical route per business surface; variants are compositions, not duplicates. | Draft contract | Wave 0 | Frontend/Platform | Route diff | Redirect old routes where needed.
API Contracts | Separate existing endpoints from Phase 2 additions. | Frontend never invents backend contracts. | Draft contract | Wave 0 | Backend/API | OpenAPI diff | VERIFY/EXTEND rows require code confirmation.
Permissions | Define server-authoritative access. | Display role names do not authorize actions; granular permissions do. | Draft contract | Wave 0 | Security/RBAC | Permission-code map | Institution Admin/Director/CEO get Executive by permission.
Lifecycle | Define legal state transitions for governed records. | Finalized/posted data is corrected/reversed, not destructively edited. | Draft contract | Wave 0 | Domain/Backend | Transition tests | Shared pattern, domain-specific state machines.
Discrepancies | Translate MVP gaps and concept expansions into actions. | Known gaps stay explicit; no invented compliance behavior. | Draft contract | Wave 0 | All leads | Updated discrepancy register | Ghana payroll gaps remain fail-closed.
Wave 0 Gates | Define the stop/go criteria for functional implementation. | High-risk backend work cannot start with unresolved contract ambiguity. | Ready | Wave 0 | Engineering Lead | Gate checklist | Low-risk Design System work may proceed in parallel.
MFA | Phase 2 security factor decision. | TOTP + email OTP only; no SMS OTP/recovery phone verification. | Locked | Wave 2 | Security | Security design + tests | Email OTP requires hash, expiry, single-use, throttling and audit.
Dashboard Routing | Executive vs operational analytics. | Executive Dashboard for Institution Admin/Director/CEO-equivalent permission; Insights for other authorized roles; Employee Home for standard Employee. | Locked | Wave 3 | Platform/Analytics | Routing tests | Use effective permission, not literal title string.
Expenses | Current Accounting capability expanded in Phase 2. | Claim → approval → finance review → GL posting → settlement. | Locked | Wave 6 | Accounting | Expense-to-GL E2E tests | No hard delete after approval/posting.

## Screen Contract Map
Screen Contract Map — ERGX-S001–S066
Every normalized Stitch screen mapped to a canonical route, Phase 2 wave, implementation status and authority note. This sheet is the bridge from design references to engineering contracts.
Screen ID | Title | Module | Stitch Route Hint | Canonical Route | Variant Of | Wave | Priority | Contract Status | Backend Impact | Frontend Impact | RBAC / Scope | Audit / Governance | Implementation Decision | Source Note
ERGX-S001 | Login / Sign In | AUTH | /login | /login |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S002 | Institution Registration | ONBOARDING | /register | /register |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S003 | Workspace Initialization / Loading | PLATFORM | N/A | shared / transient |  | Wave 1 | P1 | DESIGN/PATTERN | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S004 | Empty, Error & Loading States | DESIGN_SYSTEM | N/A | shared / transient |  | Wave 1 | P0 | DESIGN/PATTERN | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S005 | Accounting Hub — Alternate Dashboard Concept | ACCOUNTING | /accounting | /accounting | ERGX-S010 | Wave 6 | P1 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S006 | Accounts Payable — Bulk Governance Actions | ACCOUNTING | /accounting/ap | /accounting/ap | ERGX-S009 | Wave 6 | P2 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S007 | Compliance Audit Trail — Alternate Concept | AUDIT | /audit | /audit | ERGX-S011 | Wave 2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S008 | Bank Reconciliation — Transaction Matching | ACCOUNTING | /accounting/bank-reconciliation/:sessionId | /accounting/bank-reconciliation/:sessionId | ERGX-S012 | Wave 7 | P1 | VERIFY/EXTEND | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S009 | Accounts Payable — Overview & Approval Queue | ACCOUNTING | /accounting/ap | /accounting/ap |  | Wave 2 | P1 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S010 | Accounting Dashboard | ACCOUNTING | /accounting | /accounting |  | Wave 6 | P1 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S011 | Audit Trail | AUDIT | /audit | /audit |  | Wave 2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S012 | Bank Reconciliation — Overview | ACCOUNTING | /accounting/bank-reconciliation | /accounting/bank-reconciliation |  | Wave 7 | P1 | VERIFY/EXTEND | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S013 | Executive Dashboard | REPORTS | /executive | /executive |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S014 | HR Dashboard | CORE_HR | /hr/dashboard | /hr/dashboard |  | Wave 3 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S015 | Employees — List & Detail Drawer | CORE_HR | /employees | /employees |  | Wave 0/2 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S016 | Budgets | ACCOUNTING | /accounting/budgets | /accounting/budgets |  | Wave 7 | P2 | VERIFY/EXTEND | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S017 | Home — Daily Workspace | HOME | /home | /home |  | Wave 3 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S018 | General Ledger | ACCOUNTING | /accounting/general-ledger | /accounting/general-ledger |  | Wave 6 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S019 | Financial Reports | ACCOUNTING | /accounting/financial-reports | /accounting/financial-reports |  | Wave 7 | P2 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S020 | Accounts Receivable | ACCOUNTING | /accounting/ar | /accounting/ar |  | Wave 6 | P1 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S021 |  | Leave | /leave | /leave |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S022 |  | Attendance | /attendance | /attendance |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S023 |  | Attendance | /attendance/adjustments/:adjustmentId | /attendance/adjustments/:adjustmentId |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S024 |  | HR / Employee Management | /employees/:employeeId | /employees/:employeeId |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S025 |  | Employee Self-Service | /my-workspace/emergency-contacts | /my-workspace/emergency-contacts |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S026 |  | Recruitment | /recruitment/candidates/:candidateId | /recruitment/candidates/:candidateId |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S027 |  | Settings / Approvals | /settings/approval-workflows | /settings/approval-workflows |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S028 |  | Recruitment | /recruitment/requisitions/new | /recruitment/requisitions/new |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S029 |  | Accounting / Accounts Receivable | /accounting/ar/invoices/:invoiceId | /accounting/ar/invoices/:invoiceId |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S030 |  | Recruitment / Public Careers | /careers/jobs/:jobId/apply | /careers/jobs/:jobId/apply |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S031 |  | Reports & Analytics | /insights | /insights |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S032 |  | Payroll | /payroll/runs/:runId | /payroll/runs/:runId |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S033 |  | Payroll | /payroll | /payroll |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S034 |  | Recruitment | /recruitment/interviews/new | /recruitment/interviews/new |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S035 |  | Employee Self-Service / Leave | /my-workspace/leave | /my-workspace/leave |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S036 |  | Employee Self-Service / Payroll | /my-workspace/payslips | /my-workspace/payslips |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S037 |  | Employee Self-Service / Attendance | /my-workspace/attendance | /my-workspace/attendance |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S038 |  | Employee Self-Service / HR | /my-workspace/profile | /my-workspace/profile |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S039 |  | Accounting / General Ledger | /accounting/journals/:journalId | /accounting/journals/:journalId |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S040 |  | Leave / Approvals | /leave/requests/:requestId/review | /leave/requests/:requestId/review |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S041 | Module Management | Settings / Platform | /settings/modules | /settings/modules |  | Wave 2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S042 | Offer Management | Recruitment | /recruitment/offers/:offerId | /recruitment/offers/:offerId |  | Wave 4 | P1 | VERIFY | Recruitment 2.0 extensions where concept exceeds MVP. | Rebuild/refine against Design System v2. | Recruitment granular permissions. | Create/stage/decision history audited. | Implement/extend | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S043 | Security Center | Security / Self Service | /security | /security |  | Wave 2 | P0 | VERIFY/EXTEND | Email OTP challenge + session management extensions. | Security center UI. | user.manage_own_security | Mandatory security audit. | Implement | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S044 | Roles & Permissions | Settings / RBAC | /settings/roles | /settings/roles |  | Wave 2 | P0 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S045 | Institution Profile | Settings / Institution | /settings/institution | /settings/institution |  | Wave 2 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S046 | Users & Access | Users & Access | /users-access | /users-access |  | Wave 2 | P0 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S047 | Employee Home | Self Service | /my-workspace | /my-workspace |  | Wave 3 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S048 | Request Leave | Leave / Self Service | /my-workspace/leave/request | /my-workspace/leave/request |  | Wave 0/2 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S049 | My Documents | Self Service / Documents | /my-workspace/documents | /my-workspace/documents |  | Wave 3 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S050 | Personal Preferences | Self Service / Platform | /preferences | /preferences |  | Wave 0/2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S051 | Vendor Bill Detail | Accounting / Accounts Payable | /accounting/ap/bills/:billId | /accounting/ap/bills/:billId |  | Wave 6 | P1 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S052 | Budget Detail — Academic Affairs | Accounting / Budgets | /accounting/budgets/:budgetId | /accounting/budgets/:budgetId |  | Wave 7 | P2 | VERIFY/EXTEND | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S053 | Job Requisition Detail | Recruitment | /recruitment/requisitions/:requisitionId | /recruitment/requisitions/:requisitionId |  | Wave 4 | P1 | VERIFY/EXTEND | Recruitment 2.0 extensions where concept exceeds MVP. | Rebuild/refine against Design System v2. | Recruitment granular permissions. | Create/stage/decision history audited. | Implement/extend | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S054 | Financial Report Detail — Statement of Financial Position | Accounting / Financial Reports | /accounting/financial-reports/:reportId | /accounting/financial-reports/:reportId |  | Wave 7 | P2 | VERIFY | Accounting/finance API extension where needed. | Accounting UI implementation. | Finance/accounting granular permissions. | Mandatory for financial mutations. | Implement staged | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S055 | Reports & Analytics Catalogue | Reports & Analytics | /reports | /reports |  | Wave 8 | P2 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S056 | Notification Center | Platform / Notifications | /notifications | /notifications |  | Wave 2 | P0 | VERIFY/EXTEND | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S057 | Recruitment Dashboard | Recruitment | /recruitment | /recruitment |  | Wave 4 | P1 | VERIFY | Recruitment 2.0 extensions where concept exceeds MVP. | Rebuild/refine against Design System v2. | Recruitment granular permissions. | Create/stage/decision history audited. | Implement/extend | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S058 | Global Search | Platform / Search | /search | /search |  | Wave 2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S059 | Governed Empty, Error & Loading States | Design System / Platform | shared | shared |  | Wave 1 | P0 | DESIGN/PATTERN | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S060 | Confirmation Dialog Patterns | Design System / Platform | shared | shared |  | Wave 1 | P0 | DESIGN/PATTERN | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S061 | Workflow Transitions & Correction Handoffs | Governance / Platform | shared governance pattern | shared governance pattern |  | Wave 0/2 | P0 | VERIFY/EXTEND | Shared governance conventions; no universal business table. | Reusable lifecycle/timeline/action primitives. | Domain-specific permissions. | Mandatory on governed transitions. | Adopt as shared pattern | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S062 | Record Actions & Lifecycle States | Governance / HR pattern | shared lifecycle pattern | shared lifecycle pattern |  | Wave 0/2 | P0 | VERIFY/EXTEND | Shared governance conventions; no universal business table. | Reusable lifecycle/timeline/action primitives. | Domain-specific permissions. | Mandatory on governed transitions. | Adopt as shared pattern | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S063 | Employee Home — Operational Variant | Self Service | /my-workspace | /my-workspace | ERGX-S047 | Wave 3 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S064 | Approvals — Governance Review Variant | Approvals / Platform | /approvals | /approvals | ERGX-S066 | Wave 2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative. Source export lacks screen.png; use HTML/DESIGN.md.
ERGX-S065 | Employee Directory — Filter Drawer Variant | Human Resources | /employees | /employees | ERGX-S065 | Wave 3 | P1 | VERIFY | Reuse HR/self-service APIs; extend governed workflows where noted. | Implement/refine responsive screens. | Own-vs-admin scope enforced server-side. | Mutations and approvals audited. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.
ERGX-S066 | Approvals Inbox — Pending Decisions | Approvals / Platform | /approvals | /approvals |  | Wave 2 | P1 | VERIFY | Minimal or platform support. | Implement/refine. | Permission/module-aware. | As applicable. | Implement/refine | Stitch visual reference; backend/domain contracts remain authoritative.

## Canonical Routes
Canonical Route Inventory
Canonical route proposal reconciled from the 66 Stitch references. Duplicate visual concepts intentionally map to one business route.
Route ID | Canonical Surface | Canonical Route | Supporting Screen IDs | Current Status | Module | Required Permission | Landing Eligible | Wave | Variant Rule | Reconciliation Action
RT-001 | Accounting Hub | /accounting | ERGX-S005, ERGX-S010 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 6 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-002 | Accounts Payable | /accounting/ap | ERGX-S006, ERGX-S009 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 2 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-003 | Vendor Bill Detail | /accounting/ap/bills/:billId | ERGX-S051 | VERIFY | Accounting / Accounts Payable | accounting/module-specific | No | Wave 6 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-004 | Accounts Receivable | /accounting/ar | ERGX-S020 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 6 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-005 |  | /accounting/ar/invoices/:invoiceId | ERGX-S029 | VERIFY | Accounting / Accounts Receivable | accounting/module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-006 | Bank Reconciliation — Overview | /accounting/bank-reconciliation | ERGX-S012 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 7 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-007 | Bank Reconciliation — Transaction Matching | /accounting/bank-reconciliation/:sessionId | ERGX-S008 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 7 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-008 | Budgets | /accounting/budgets | ERGX-S016 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 7 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-009 | Budget Detail — Academic Affairs | /accounting/budgets/:budgetId | ERGX-S052 | VERIFY | Accounting / Budgets | accounting/module-specific | No | Wave 7 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-010 | Financial Reports | /accounting/financial-reports | ERGX-S019 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 7 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-011 | Financial Report Detail — Statement of Financial Position | /accounting/financial-reports/:reportId | ERGX-S054 | VERIFY | Accounting / Financial Reports | accounting/module-specific | No | Wave 7 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-012 | General Ledger | /accounting/general-ledger | ERGX-S018 | VERIFY | ACCOUNTING | accounting/module-specific | No | Wave 6 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-013 |  | /accounting/journals/:journalId | ERGX-S039 | VERIFY | Accounting / General Ledger | accounting/module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-014 | Approvals | /approvals | ERGX-S064, ERGX-S066 | VERIFY | Approvals / Platform | approval.inbox.view | No | Wave 2 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-015 |  | /attendance | ERGX-S022 | VERIFY | Attendance | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-016 |  | /attendance/adjustments/:adjustmentId | ERGX-S023 | VERIFY | Attendance | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-017 | Compliance Audit Trail | /audit | ERGX-S007, ERGX-S011 | VERIFY | AUDIT | module-specific | No | Wave 2 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-018 |  | /careers/jobs/:jobId/apply | ERGX-S030 | VERIFY | Recruitment / Public Careers | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-019 | Employees | /employees | ERGX-S015, ERGX-S065 | VERIFY | CORE_HR | module-specific | No | Wave 0/2 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-020 |  | /employees/:employeeId | ERGX-S024 | VERIFY | HR / Employee Management | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-021 | Executive Dashboard | /executive | ERGX-S013 | VERIFY | REPORTS | dashboard.executive.view | Yes | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-022 | Home — Daily Workspace | /home | ERGX-S017 | KEEP/VERIFY | HOME | module-specific | Yes | Wave 3 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-023 | HR Dashboard | /hr/dashboard | ERGX-S014 | VERIFY | CORE_HR | module-specific | No | Wave 3 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-024 |  | /insights | ERGX-S031 | VERIFY | Reports & Analytics | analytics.insights.view + source permissions | Yes | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-025 |  | /leave | ERGX-S021 | VERIFY | Leave | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-026 |  | /leave/requests/:requestId/review | ERGX-S040 | VERIFY | Leave / Approvals | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-027 | Login / Sign In | /login | ERGX-S001 | KEEP/VERIFY | AUTH | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-028 | Employee Home | /my-workspace | ERGX-S047, ERGX-S063 | VERIFY | Self Service | own-record self-service | Yes | Wave 3 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-029 |  | /my-workspace/attendance | ERGX-S037 | VERIFY | Employee Self-Service / Attendance | own-record self-service | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-030 | My Documents | /my-workspace/documents | ERGX-S049 | VERIFY | Self Service / Documents | own-record self-service | No | Wave 3 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-031 |  | /my-workspace/emergency-contacts | ERGX-S025 | VERIFY | Employee Self-Service | own-record self-service | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-032 |  | /my-workspace/leave | ERGX-S035 | VERIFY | Employee Self-Service / Leave | own-record self-service | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-033 | Request Leave | /my-workspace/leave/request | ERGX-S048 | VERIFY | Leave / Self Service | own-record self-service | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-034 |  | /my-workspace/payslips | ERGX-S036 | VERIFY | Employee Self-Service / Payroll | own-record self-service | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-035 |  | /my-workspace/profile | ERGX-S038 | VERIFY | Employee Self-Service / HR | own-record self-service | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-036 | Notification Center | /notifications | ERGX-S056 | VERIFY | Platform / Notifications | module-specific | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-037 |  | /payroll | ERGX-S033 | VERIFY | Payroll | payroll.* | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-038 |  | /payroll/runs/:runId | ERGX-S032 | VERIFY | Payroll | payroll.* | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-039 | Personal Preferences | /preferences | ERGX-S050 | VERIFY | Self Service / Platform | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-040 | Recruitment Dashboard | /recruitment | ERGX-S057 | VERIFY | Recruitment | recruitment/module-specific | No | Wave 4 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-041 |  | /recruitment/candidates/:candidateId | ERGX-S026 | VERIFY | Recruitment | recruitment/module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-042 |  | /recruitment/interviews/new | ERGX-S034 | VERIFY | Recruitment | recruitment/module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-043 | Offer Management | /recruitment/offers/:offerId | ERGX-S042 | VERIFY | Recruitment | recruitment/module-specific | No | Wave 4 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-044 | Job Requisition Detail | /recruitment/requisitions/:requisitionId | ERGX-S053 | VERIFY | Recruitment | recruitment/module-specific | No | Wave 4 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-045 |  | /recruitment/requisitions/new | ERGX-S028 | VERIFY | Recruitment | recruitment/module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-046 | Institution Registration | /register | ERGX-S002 | VERIFY | ONBOARDING | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-047 | Reports & Analytics Catalogue | /reports | ERGX-S055 | VERIFY | Reports & Analytics | module-specific | No | Wave 8 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-048 | Global Search | /search | ERGX-S058 | VERIFY | Platform / Search | module-specific | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-049 | Security Center | /security | ERGX-S043 | VERIFY | Security / Self Service | user.manage_own_security | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-050 |  | /settings/approval-workflows | ERGX-S027 | VERIFY | Settings / Approvals | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-051 | Institution Profile | /settings/institution | ERGX-S045 | VERIFY | Settings / Institution | module-specific | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-052 | Module Management | /settings/modules | ERGX-S041 | VERIFY | Settings / Platform | module-specific | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-053 | Roles & Permissions | /settings/roles | ERGX-S044 | VERIFY | Settings / RBAC | role.manage | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-054 | Users & Access | /users-access | ERGX-S046 | VERIFY | Users & Access | membership.manage | No | Wave 2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-055 | Governed Empty, Error & Loading States | shared | ERGX-S059, ERGX-S060 | VERIFY | Design System / Platform | module-specific | No | Wave 1 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-056 | Workspace Initialization / Loading | shared / transient | ERGX-S003, ERGX-S004 | VERIFY | PLATFORM | module-specific | No | Wave 1 | Merge variants into one canonical implementation. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-057 | Workflow Transitions & Correction Handoffs | shared governance pattern | ERGX-S061 | VERIFY | Governance / Platform | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.
RT-058 | Record Actions & Lifecycle States | shared lifecycle pattern | ERGX-S062 | VERIFY | Governance / HR pattern | module-specific | No | Wave 0/2 | Single reference. | Inspect actual router and replace duplicate/legacy routes with redirects or canonical navigation.

## API Contracts
Wave 0 API Contract Inventory
Proposed/expected contract surface for Phase 2. Exact existing paths must be reconciled to current OpenAPI before implementation; do not rename functioning APIs just to match this sheet.
API ID | Capability | Proposed / Expected Endpoint | Method | Status | Module | Request Contract | Response Contract | Authorization | Audit | Wave | Guardrail
API-001 | Current user/institution context | /api/v1/me/context/ | GET | VERIFY/EXTEND | PLATFORM | Active institution selector/context | User, memberships, active institution, roles, permissions, enabled modules | Authenticated membership | Security context optional | Wave 2 | Context selection never grants access.
API-002 | Executive dashboard | /api/v1/dashboards/executive/ | GET | NEW/EXTEND | REPORTS | period/location filters | Module-aware KPI/series blocks | dashboard.executive.view + source perms | Read optional | Wave 3 | Omit disabled-module metrics; no fake zeroes.
API-003 | Insights | /api/v1/insights/ | GET | NEW/EXTEND | REPORTS | period/department/location filters | Permission-filtered analytics blocks | analytics.insights.view + source perms | Read optional | Wave 3 | Role title not used as authorization.
API-004 | Global search | /api/v1/search/ | GET | VERIFY/EXTEND | PLATFORM | q + filters | Grouped permission-scoped results + controlled route metadata | search.use + source perms | Optional | Wave 2 | Authorize before retrieval.
API-005 | Notifications | /api/v1/notifications/ | GET/PATCH | NEW/EXTEND | PLATFORM | filters/read/archive flags | Recipient-scoped notifications | notification.view_own/manage_own | Optional state audit | Wave 2 | Controlled internal deep links only.
API-006 | Notification preferences | /api/v1/notification-preferences/ | GET/PATCH | NEW | PLATFORM | in-app/email categories | Preference object | user.manage_own_preferences | Optional | Wave 2 | No SMS channel.
API-007 | Email OTP create | /api/v1/auth/email-otp/challenge/ | POST | NEW | SECURITY | purpose | challenge_id, masked destination, expiry | Login/auth context | Mandatory | Wave 2 | Hash OTP; rate limit; single-use.
API-008 | Email OTP verify | /api/v1/auth/email-otp/verify/ | POST | NEW | SECURITY | challenge_id + OTP | verified continuation | Challenge scoped | Mandatory | Wave 2 | Expiry and max attempts enforced.
API-009 | Session list/revoke | /api/v1/security/sessions/ ; /:id/revoke/ | GET/POST | NEW | SECURITY | session id for revoke | Device/browser/last_seen/revoked | user.manage_own_security | Mandatory revoke audit | Wave 2 | Revoke must invalidate actual authorization.
API-010 | Roles & permissions | /api/v1/access/roles/ ; /:id/permissions/ | GET/PATCH | VERIFY/EXTEND | RBAC | Role metadata / permission diff | System/custom role + granular permissions | role.view/manage | Mandatory changes | Wave 2 | System roles protected.
API-011 | Access requests | /api/v1/access/requests/ | GET/POST | NEW | RBAC | requested access + reason | Request + approval state | access.request + membership manage | Mandatory | Wave 2 | Governed approval.
API-012 | Approval workflows | /api/v1/approval-workflows/ | GET/POST/PATCH | NEW/EXTEND | PLATFORM | module, trigger, ordered stages | Workflow definition | approval.workflow.manage | Mandatory | Wave 2 | Supported approver types only initially.
API-013 | Approval inbox/decision | /api/v1/approvals/ ; /:id/decision/ | GET/POST | VERIFY/EXTEND | PLATFORM | filters / decision + comment | Approval request/state | approval.inbox.view + step authority | Mandatory decisions | Wave 2 | Batch decisions require per-record authorization.
API-014 | Job requisitions | /api/v1/recruitment/requisitions/ | GET/POST/PATCH | NEW | RECRUITMENT | Job/hiring plan fields | Requisition record | requisition.* | Mandatory | Wave 4 | Approval before publish when configured.
API-015 | Candidate evaluation | /api/v1/recruitment/applications/:id/evaluations/ | GET/POST | NEW/EXTEND | RECRUITMENT | criteria scores/comments | Per-evaluator results | candidate.evaluate | Mandatory | Wave 4 | Criteria configurable.
API-016 | Interview scheduling | /api/v1/recruitment/interviews/ | POST/PATCH | VERIFY/EXTEND | RECRUITMENT | datetime/timezone/panel/type/link | Interview state | interview.manage | Mandatory | Wave 4 | No fake Teams/Google availability.
API-017 | Offer actions | /api/v1/recruitment/offers/:id/action/ | POST | VERIFY/EXTEND | RECRUITMENT | submit/send/response/convert | Offer state + lineage | offer-specific permissions | Mandatory | Wave 4 | Hire conversion preserves lineage.
API-018 | Leave policy checks | /api/v1/leave/requests/:id/policy-checks/ | GET | NEW/EXTEND | LEAVE | None | PASS/FAIL/WARNING/NOT_EVALUATED checks | leave.view/manage | Optional | Wave 3 | Unknown ≠ compliant.
API-019 | Leave review | /api/v1/leave/requests/:id/review/ | POST | VERIFY/EXTEND | LEAVE | approve/decline/request_changes/delegate | Updated request/approval | leave.approve | Mandatory | Wave 3 | Evidence/policy requirements enforced.
API-020 | Attendance adjustments | /api/v1/attendance/adjustments/ | GET/POST | NEW/EXTEND | ATTENDANCE | date/original/requested/reason/evidence | Adjustment record | own/admin adjustment perms | Mandatory | Wave 3 | Check finalized payroll dependency.
API-021 | Attendance adjustment review | /api/v1/attendance/adjustments/:id/review/ | POST | NEW | ATTENDANCE | decision/comment/delegate | Updated adjustment + effects | attendance.adjustment.review | Mandatory | Wave 3 | No silent historical payroll rewrite.
API-022 | Payroll validate/exceptions | /api/v1/payroll/runs/:id/validate/ ; /exceptions/ | POST/GET | NEW/EXTEND | PAYROLL | validation request | Run status + structured exceptions | payroll.validate/view_run | Mandatory progression | Wave 5 | Blocking exceptions prevent progression.
API-023 | Resolve payroll exception | /api/v1/payroll/exceptions/:id/resolve/ | POST | NEW | PAYROLL | resolution/note/reference | Resolved exception | payroll.resolve_exception | Mandatory | Wave 5 | Fix true source-data errors rather than bypass.
API-024 | Expense claims | /api/v1/accounting/expenses/ | GET/POST/PATCH | VERIFY/EXTEND | ACCOUNTING | claim header/items/attachments | Expense claim | expense.* | Mandatory | Wave 6 | Institution scoped.
API-025 | Expense action/post/settle | /api/v1/accounting/expenses/:id/action/ ; /post/ ; /settle/ | POST | NEW/EXTEND | ACCOUNTING | workflow/posting/settlement payload | State + journal/settlement links | expense action permissions | Mandatory | Wave 6 | Fail closed on missing mapping/closed period.
API-026 | Bank statements/reconciliation | /api/v1/accounting/bank-statements/ ; /reconciliations/ | GET/POST | NEW | ACCOUNTING | statement import/session fields | Statements, lines, sessions | bank.reconcile | Mandatory | Wave 7 | CSV/import/manual matching first.
API-027 | Reconciliation match | /api/v1/accounting/reconciliations/:id/matches/ | POST/DELETE | NEW | ACCOUNTING | bank line + book entry | Match state | bank.reconcile | Mandatory | Wave 7 | All match/unmatch actions audited.
API-028 | Budgets | /api/v1/accounting/budgets/ | GET/POST/PATCH | NEW | ACCOUNTING | period/dimensions/lines | Budget detail | budget.* | Mandatory | Wave 7 | Actual from posted GL only; no committed without source.
API-029 | Financial report run | /api/v1/accounting/financial-reports/:id/run/ | POST | VERIFY/EXTEND | ACCOUNTING | parameters | Generated report/data | financial_report.run | Mandatory generation | Wave 7 | Export formats limited to actual exporters.

## Permission Matrix
Permission Matrix
Role presets shown here are defaults for planning. Backend granular permissions are the actual authority; custom roles may receive equivalent rights explicitly.
Permission / Capability | Institution Admin | Director / CEO | HR Admin | Finance Manager | Accountant | Recruitment Officer | Payroll Officer | Auditor | Employee | Rule
dashboard.executive.view | Y | Y | N | N | N | N | N | N | N | Executive strategic dashboard; custom role may receive explicitly.
analytics.insights.view | Optional | Optional | Y | Y | Y | Y | Y | Y read-scope | N | Source permissions still filter data.
employee.view/manage | Y | Optional read | Y | Scoped read | Scoped read | Scoped read | Scoped read | Read | Own/subset | Admin users cannot use admin HR powers on own protected HR record.
requisition.create/manage | Y | Optional | Y | N | N | Y | N | Read if granted | N | Requires Recruitment module.
candidate.evaluate | Optional | Optional | Y | N | N | Y | N | Read if granted | N | May also be scoped by panel membership.
leave.approve | Y | Optional | Y | N | N | N | N | Read | N | Approval workflow/manager relation authorizes.
attendance.adjustment.review | Y | Optional | Y | N | N | N | N | Read | N | Delegation supported via workflow.
payroll.view/manage | Y | Summary optional | Scoped | Y | Y | N | Y | Read | Own payslip only | Sensitive fields require explicit permission.
payroll.resolve_exception | Y | Optional | Scoped | Y | Y | N | Y | Read | N | Match responsibility to exception type.
journal.create/approve/post | Y | Optional read | N | Y | Y if assigned | N | N | Read | N | Segregation of duties may separate create/approve/post.
ap/ar.manage | Y | Optional read | N | Y | Y | N | N | Read | N | Accounting module required.
expense.create_own | Y if employee | Y if employee | Y if employee | Y if employee | Y if employee | Y if employee | Y if employee | Optional | Y | Self-service permission.
expense.approve_manager | Y | Optional | Manager-dependent | Manager-dependent | Manager-dependent | Manager-dependent | Manager-dependent | N | N | Approval engine resolves actual approver.
expense.finance_review/post | Y | N | N | Y | Y if granted | N | N | Read | N | Requires GL/mapping authority.
bank.reconcile | Y | Optional | N | Y | Y | N | N | Read | N | Finance operational access.
budget.manage/approve | Y | Optional | N | Y | Scoped | N | N | Read | N | Separate manage/approve where required.
approval.workflow.manage | Y | N | Optional | Optional | N | N | N | Read | N | Highly privileged institution setting.
role.manage | Y | N | N | N | N | N | N | Read | N | System roles protected.
membership.manage | Y | N | Optional | N | N | N | N | Read | N | Invites/access changes audited.
audit.view | Y | Optional | Scoped | Scoped | Scoped | Scoped | Scoped | Y | Own security activity | Audit field visibility can be further restricted.
user.manage_own_security | Y | Y | Y | Y | Y | Y | Y | Y | Y | Password, TOTP, email OTP, sessions.

## Lifecycle Matrix
Governed Lifecycle Matrix
Target Phase 2 lifecycle contracts. Existing enum/state names should be reconciled, not blindly renamed. Shared UI patterns do not imply one universal state table.
Record | State | Allowed Next | Actor | Preconditions | Editable? | Hard Delete? | Correction / Reversal | Audit
Job Requisition | DRAFT | SUBMITTED | Creator/Recruitment | Required fields complete | Yes | Yes if unreferenced | Edit draft | Mandatory
Job Requisition | SUBMITTED | APPROVED / REJECTED / CHANGES_REQUESTED | Approver | Approval workflow | No except governed return | No | Return/revise through workflow | Mandatory
Job Requisition | APPROVED | OPEN / CLOSED | Recruitment | Approval complete | Limited | No | New revision/close | Mandatory
Application | SUBMITTED | SCREENING / WITHDRAWN | Recruitment/Candidate where allowed | Submission valid | Limited | No | Linked correction/history | Mandatory
Application | SCREENING | INTERVIEW / REJECTED | Recruitment | Configured evaluation | Limited | No | Linked history | Mandatory
Application | INTERVIEW | OFFER / REJECTED | Recruitment | Interview process complete | Limited | No | Linked history | Mandatory
Application | OFFER | HIRED / REJECTED / WITHDRAWN | Recruitment | Offer response | Limited | No | Linked history | Mandatory
Application | HIRED | CONVERTED_TO_EMPLOYEE | System/HR | Employee conversion succeeds | Read-only | No | Successor Employee record | Mandatory lineage
Leave Request | DRAFT | SUBMITTED / CANCELLED | Employee | Required fields complete | Yes | Yes if safe | Edit draft | Mandatory
Leave Request | SUBMITTED | APPROVED / DECLINED / CHANGES_REQUESTED / CANCELLED | Approver | Policy + approval checks | No | No | Request changes/new revision | Mandatory
Attendance Adjustment | DRAFT | SUBMITTED | Employee/Admin | Reason/evidence if required | Yes | Yes if safe | Edit draft | Mandatory
Attendance Adjustment | SUBMITTED | APPROVED / DECLINED / CHANGES_REQUESTED | Reviewer | Schedule/leave/payroll checks | No | No | New linked adjustment if later change | Mandatory
Payroll Run | DRAFT | VALIDATING | Payroll | Data prepared | Yes | Only if safe | Edit draft | Mandatory
Payroll Run | VALIDATING | VALIDATION_FAILED / READY_FOR_APPROVAL | System | Validation rules execute | No | No | Fix source data/exceptions | Mandatory
Payroll Run | READY_FOR_APPROVAL | APPROVAL_PENDING | Payroll | No blocking exceptions | No | No | Controlled return to draft | Mandatory
Payroll Run | APPROVAL_PENDING | APPROVED / REJECTED | Approver | Approval workflow | No | No | Rejected run returns to correction state | Mandatory
Payroll Run | APPROVED | FINALIZED | Authorized Payroll/Finance | Configuration complete | No | No | Linked reversal/adjustment only after finalization | Mandatory
Payroll Run | FINALIZED | PAID | Authorized Payroll/Finance | Payment recorded/confirmed | No | No | Linked adjustment/reversal | Mandatory
Journal | DRAFT | APPROVAL_PENDING / POSTED | Finance | Balanced, open period, mappings resolved | Yes | Yes if safe | Edit draft | Mandatory
Journal | APPROVAL_PENDING | APPROVED / REJECTED | Approver | Balanced + workflow | No | No | Controlled return | Mandatory
Journal | APPROVED | POSTED | Poster | Open period + balance | No | No | Post | Mandatory
Journal | POSTED | — | — | Immutable | No | No | Reversing/correcting journal | Mandatory
Expense Claim | DRAFT | SUBMITTED / CANCELLED | Employee | Items/receipts valid | Yes | Yes if safe | Edit draft | Mandatory
Expense Claim | SUBMITTED | MANAGER_APPROVED / DECLINED / CHANGES_REQUESTED | Approver | Approval workflow | No | No | Request changes | Mandatory
Expense Claim | MANAGER_APPROVED | FINANCE_REVIEW | System/Finance | Manager approval complete | Finance coding only | No | Finance review | Mandatory
Expense Claim | FINANCE_REVIEW | APPROVED / CHANGES_REQUESTED / DECLINED | Finance | Mappings/policy/tax/open period | Limited | No | Request changes | Mandatory
Expense Claim | APPROVED | POSTED | Finance poster | Balanced mapping resolved | No | No | Posting creates linked journal | Mandatory
Expense Claim | POSTED | SETTLED | Finance | Settlement recorded | No | No | Accounting reversal/adjustment | Mandatory
Bank Reconciliation Session | DRAFT | IN_PROGRESS | Finance | Bank account + statement selected | Yes | Yes if empty | Edit session | Mandatory
Bank Reconciliation Session | IN_PROGRESS | COMPLETED | Finance | Reconciliation invariants pass | Match state only | No | Governed reopen/new session | Mandatory

## Discrepancy Actions
Phase 2 Discrepancy & Action Register
Known MVP limitations plus concept-driven extensions converted into explicit Phase 2 actions. This preserves the fail-closed and no-invention rules established for ErgonX.
ID | Gap / Discrepancy | Current Position | Phase 2 Decision | Required Action | Acceptance Evidence | Wave | Priority | Status | Guardrail
D2-001 | HOME-001: not every create workflow emits shared activity/reference events | Known P1 | Resolve selectively | Standardize designated business activity events/reference contracts | E2E samples | Wave 2/3 | P1 | Open | Do not emit noise for trivial UI reads.
D2-002 | OPS-001: arbitrary typed imports/exports need handlers | Known P1 | Keep explicit handlers | Add only supported Phase 2 import/export handlers | Handler tests | Wave 6/7 | P1 | Open | No generic unsafe importer.
D2-003 | REPORT-001: CSV only; no XLSX/PDF | Accepted MVP | Stage enhancement | Expose only implemented exporters | Export tests | Wave 7/8 | P2 | Open | Do not advertise unsupported formats.
D2-004 | ERD-005: account provenance/system mapping gap | Known P1 | Resolve before deeper accounting preset/reporting work | Persist account-template/system mapping provenance | Migration/mapping tests | Wave 6 | P0 | Open | Supports safer Ghana preset evolution.
D2-005 | Ghana payroll statutory gaps: minimum wage basis | Known limitation | Remain fail-closed | Add explicit configurable/verified basis only | Scenario tests | Wave 5 | P1 | Open | Never guess statutory values.
D2-006 | Ghana payroll pension eligibility/exemption gaps | Known limitation | Refine configuration/validation | Represent eligibility/exemption explicitly | Scenario tests | Wave 5 | P1 | Open | Version under GH preset.
D2-007 | Ghana payroll mid-period proration gaps | Known limitation | Enhance | Configurable proration/effective dates | Unit tests | Wave 5 | P1 | Open | No hidden proration rule.
D2-008 | Ghana payroll relief timing/validation gaps | Known limitation | Enhance when verified | Model evidence/effective periods | Scenario tests | Wave 5 | P1 | Open | No legal certification claim.
D2-009 | Ghana payroll overtime threshold validation unresolved | Known limitation | Keep configurable | Separate institution overtime policy from statutory/localization rule | Validation tests | Wave 5 | P1 | Open | No inferred threshold.
D2-010 | Email OTP not in current confirmed MFA feature set | New Phase 2 | Add | Implement secure email OTP challenge/verify flow | Security tests + audit | Wave 2 | P0 | Open | TOTP remains supported; SMS excluded.
D2-011 | Server-tracked session revocation not confirmed | New Phase 2 | Add | Track session/token families and revoke | Security E2E | Wave 2 | P0 | Open | Revocation must actually invalidate auth.
D2-012 | Approval workflow depth exceeds MVP simple approvals | New/Extend | Add controlled engine | Supported triggers/stages/approver types/delegation/escalation | Workflow E2E | Wave 2 | P0 | Open | Not a generic no-code automation platform.
D2-013 | JobRequisition absent from MVP | Superseded MVP decision | Add | Implement requisition→approval→posting lifecycle | Recruitment E2E | Wave 4 | P1 | Open | Preserve JobPosting compatibility.
D2-014 | Structured scorecards/evaluation templates deeper than current model | New/Extend | Add | Template/criterion/submission models | RBAC + evaluation tests | Wave 4 | P1 | Open | Configurable criteria.
D2-015 | External calendar/Teams availability not integrated | Future integration | Defer integration | Internal scheduler first | No fake availability | Wave 8 | P2 | Deferred | Manual meeting link storage okay.
D2-016 | Attendance adjustment governance deeper than current module | New/Extend | Add | Adjustment/evidence/validation/approval models | E2E tests | Wave 3 | P1 | Open | Check finalized payroll dependency.
D2-017 | Structured payroll exception engine not confirmed at concept depth | New/Extend | Add | Validation rules/exceptions/progression gates | Payroll suite | Wave 5 | P0 | Open | Blocking exceptions stop progression.
D2-018 | Expenses exists but needs governed end-to-end workflow | Extend | Implement Expense Management 2.0 | Claim/items/receipts/policy/approval/finance review/post/settle | Expense-to-GL E2E | Wave 6 | P0 | Open | No hard delete after approval/posting.
D2-019 | Manual/import bank reconciliation not confirmed at concept depth | New/Extend | Add | Statement import/lines/sessions/matches | Reconciliation E2E | Wave 7 | P1 | Open | Bank feeds later.
D2-020 | Budgeting is new accounting capability | New | Add after Accounting 2.0 core | Budget/lines/revisions/actual/variance | Budget-to-GL tests | Wave 7 | P2 | Planned | No committed amount without source.
D2-021 | Report catalogue/scheduling/sharing exceeds MVP reports | New/Extend | Stage | Catalogue → saved configs → sharing → scheduling | Reporting tests | Wave 8 | P2 | Planned | No Power BI-style builder initially.
D2-022 | Concepts include Procurement/Learning/Performance/Benefits references | Future scope only | Do not silently implement | Keep feature flags/navigation absent unless separately approved | Scope review | Wave 8+ | P2 | Deferred | PO examples are illustrative.
D2-023 | Concepts show subscription/institution-plan packaging | Future commercial layer | Defer | Keep module enablement/dependencies only | Settings test | Wave 8+ | P2 | Deferred | No billing-plan mechanics yet.
D2-024 | Stitch uses production-like sample data | Design artifact | Prohibit in production | Use real APIs or governed states | UI acceptance | Wave 1 | P0 | Open | Demo seeds only in explicit demo/test environments.

## Wave 0 Gates
Wave 0 Exit Gates
These gates define when the technical contract is sufficiently reconciled for high-risk Phase 2 implementation. Design System work may run in parallel.
Gate | Exit Condition | Evidence | Owner | Status | Blocks | Notes
G0-01 | Canonical route map reconciled with actual frontend router | KEEP/REDIRECT/NEW route diff | Frontend Lead | Not Started | Wave 2+ navigation | No duplicate business routes.
G0-02 | API inventory reconciled to live OpenAPI/backend | VERIFY rows resolved | Backend Lead | Not Started | Functional UI wiring | Frontend may not invent endpoints.
G0-03 | Permission matrix reconciled to actual permission codes | UI action → backend permission map | Security/Backend | Not Started | RBAC-sensitive screens | No role-name-only authorization.
G0-04 | Lifecycle contracts approved for Payroll, Journal, Expense, Leave, Attendance Adjustment, Recruitment | State diagrams + transition tests | Domain Leads | Not Started | Irreversible mutations | Shared UI pattern, domain-specific rules.
G0-05 | Approval engine boundary approved | Supported triggers, approver types, delegation/escalation | Architecture/Backend | Not Started | Approval-dependent modules | Not generic workflow automation.
G0-06 | Email OTP security controls finalized | Expiry, resend cooldown, attempts, throttling, masking, audit | Security | Not Started | Email OTP release | No SMS OTP.
G0-07 | Expense-to-GL mapping contract finalized | Category→account mapping source, posting entries, closed-period behavior | Accounting/Backend | Not Started | Expense posting | No hard-coded account IDs.
G0-08 | GH-2026.1 verified/unresolved localization rules documented | Verified vs fail-closed rule list | Payroll/Research | Not Started | Ghana payroll Phase 2 | Never guess legal/statutory values.
G0-09 | 66 Stitch screens mapped to canonical routes/components | Screen IDs linked to final design frames | Design/Frontend | Not Started | Screen migration | Variants merged intentionally.
G0-10 | Critical-path test plan agreed | Unit/integration/E2E/security test matrix | QA/Engineering | Not Started | Wave 2–7 release | No high-risk progression without tests.
G0-11 | Module dependency and disabled-module behavior verified | Dependency matrix + API/UI denial tests | Backend/Frontend | Not Started | Module-aware routing | Disabled = hidden UI + blocked API; data preserved.
G0-12 | Audit event taxonomy agreed for Phase 2 mutations | Event names/actor/target/before-after requirements | Security/Audit | Not Started | Governed actions | Field-level before/after where applicable.

## Summary
Wave 0 Contract Summary
Quick control view for the Phase 2 contract pack.
Metric | Count | Priority | Discrepancies | Reconciliation Status | Count
Stitch screens mapped | 66 | P0 | 7 | Complete/Design Ready | 2
Canonical route groups | 58 | P1 | 11 | Partial | 10
API contracts listed | 29 | P2 | 6 | Remaining direct-code gates | 10
Permission capabilities | 21
Lifecycle states/transitions | 30
Discrepancy actions | 24
Wave 0 exit gates | 12
P0 discrepancy actions | 7
P1 discrepancy actions | 11
P2 discrepancy actions | 6

## Current-State Evidence
Current-State Evidence Reconciliation
Evidence-grounded findings from the current checkout context, latest discrepancy register, and authentication/onboarding specification. Later dated discrepancy resolutions supersede older current-checkout caveats.
Evidence ID | Area | Verified Current State | Engineering Implication | Confidence | Source File | Source Detail | Supersedes / Conflicts | Action | Wave
EV-001 | Frontend architecture | Active frontend is Next.js App Router with TypeScript/Tailwind/Lucide and Django `/api/v1/`; current checkout documented 106 `page.tsx` routes. | Reuse current App Router and typed API modules; do not create a parallel frontend architecture. | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md | Product shape + route/module map | None | Preserve architecture while redesigning UI. | Wave 0/1
EV-002 | API client | Shared typed API modules exist for auth, institutions, home, dashboards, employees, organization, leave, scheduling, attendance, payroll, accounting, recruitment, reports, workflows, operations, and universal search. | New Phase 2 endpoints belong in existing domain adapters/types; no one-off Axios clients. | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md | Typed integration modules | None | Use existing API client conventions. | All
EV-003 | Auth APIs | Verified auth APIs include `POST /api/v1/auth/login/`, `POST /api/v1/auth/refresh/`, and `GET /api/v1/auth/me/`. | Do not invent `/me/context/`; extend current auth/bootstrap/institution context flow instead. | High | ErgonX_Authentication_Institution_Onboarding_Backend_Specification.pdf | §2 Authentication Architecture | Earlier proposed API-001 `/me/context/` | Replace proposed context endpoint with existing bootstrap + institution APIs. | Wave 2
EV-004 | Institution context | Existing context APIs include `GET /api/v1/institutions/current/` and `/memberships/`; `X-Institution-ID` is a selector, never an access grant. | All Phase 2 APIs remain tenant-scoped server-side; switching institution re-resolves permissions/modules. | High | ErgonX_Authentication_Institution_Onboarding_Backend_Specification.pdf | §4 Institution and Tenant Context | None | Lock as mandatory backend invariant. | All
EV-005 | Bootstrap | Frontend `AuthProvider` fetches memberships, selects context and calls `/auth/bootstrap/`. | Executive/Insights routing should use effective permissions/modules returned by bootstrap rather than role-title checks. | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md | Authentication and tenant context | None | Reconcile dashboard landing logic with bootstrap. | Wave 2/3
EV-006 | RBAC/module gating | Navigation is filtered by enabled modules, role code and effective permissions, but Django remains final authority. | Frontend hiding never replaces server denial; module disabled and permission denied stay distinct states. | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md | RBAC and module behavior | None | Preserve PermissionGuard/ModuleGuard patterns and backend checks. | All
EV-007 | OpenAPI | Generated `openapi-schema.yml` validates with zero errors/warnings after schema fixes. | Use current OpenAPI as implementation truth; contract reconciliation can be mechanized against schema. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | OPENAPI-001 RESOLVED | Earlier draft VERIFY ambiguity | Treat schema as authoritative for existing APIs. | Wave 0
EV-008 | Executive dashboard | `/api/v1/dashboards/executive/` exists and is module-aware after DASH-002/DASH-003 fixes; finance/executive dashboards use posted-ledger rollups and institution currency. | Do not create a second executive endpoint. Extend existing response only for approved Phase 2 metrics. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | DASH-001/DASH-002/DASH-003 notes | Earlier proposed 'new executive endpoint' | Change API contract status from NEW/EXTEND to EXISTING/EXTEND. | Wave 3
EV-009 | Universal search | A tenant-aware global search endpoint and typed frontend adapter already exist; backend provides route hints. | Stitch Global Search should be a UI redesign/extension, not a new search subsystem. | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md | Typed integration modules | Earlier API status uncertainty | Mark search capability EXISTING/EXTEND; verify exact OpenAPI path. | Wave 2
EV-010 | Notifications | Notification backend, route hints, schema declarations and frontend status affordances exist; operational depth must still be checked. | Build Notification Center on existing notification domain, extending recipient state/preferences only where absent. | Medium-High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | OPENAPI-001/UI-004 evidence | Earlier 'new notification system' framing | Reclassify as EXISTING/EXTEND. | Wave 2
EV-011 | TOTP MFA | Optional TOTP setup/confirm/disable plus login challenge already implemented. | Email OTP is additive Phase 2 work; do not replace or duplicate TOTP flows. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | UI-003 RESOLVED | None | Add email OTP alongside existing TOTP. | Wave 2
EV-012 | BFF / token security | BFF proxy with HttpOnly SameSite access/refresh cookies was implemented and validated on 2026-09-22; JavaScript no longer receives bearer tokens. | Session-management work should build on the BFF/session boundary, not revert to local-storage bearer tokens. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | PWA-002 RESOLVED | Sep-20 context doc local-storage caveat | Latest discrepancy resolution supersedes older context note. | Wave 2
EV-013 | PWA | Manifest, service worker, static offline route and production registration were restored and validated; worker excludes API/navigation/exports/JWTs/tenant data and never queues writes. | Responsive/mobile Stitch implementation can preserve the safe online-first PWA boundary. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | PWA-001 RESOLVED | Sep-20 context doc 'PWA missing' caveat | Latest discrepancy resolution supersedes older context note. | Wave 1
EV-014 | Reports export | Current reports are CSV-only; XLSX/PDF renderers and scheduled/background formatted exports are not implemented. | Hide/disable unsupported PDF/XLSX export actions in Stitch concepts until Phase 2 exporters exist. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | REPORT-001 ACCEPTED_MVP | None | Keep CSV existing; stage formatted exports later. | Wave 7/8
EV-015 | Imports/exports | Tenant-safe ImportJob/ExportJob/BackgroundJob infrastructure exists; employee and attendance imports plus report CSV export have explicit handlers. | Bank statement import should be a new explicit typed handler, not a generic importer. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | OPS-001 REVIEW | None | Reuse operations infrastructure. | Wave 7
EV-016 | Accounting | Accounting core, presets, Ghana localization, AP/AR/cash/expenses and payroll-to-accounting are delivered with documented limitations. | Phase 2 accounting screens mostly deepen existing backend domains rather than create them from scratch. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | Current module completion gate | Earlier concepts treated some finance areas as wholly new | Reclassify AP/AR/Expenses as existing/extend; reconcile bank/budget separately. | Wave 6/7
EV-017 | Recruitment | Internal ATS records and candidate document linkage already exist; no public careers portal/job-board integration/configurable assessment engine. | Requisition/evaluation depth is Phase 2 extension; public candidate portal remains later unless explicitly promoted. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | Recruitment limitation entry | None | Extend internal ATS first. | Wave 4/8
EV-018 | Recruitment target lifecycle | Approved planning specification explicitly targets Job Requisition → Approval → Job Opening → Applications → Screening → Interview → Offer → Hire → Employee conversion. | JobRequisition is a legitimate Phase 2 addition integrated with Core HR lineage. | High | ErgonX_Authentication_Institution_Onboarding_Backend_Specification.pdf | §11 Recruitment Module | None | Proceed with requisition model after actual recruitment code reconciliation. | Wave 4
EV-019 | Self-HR protection | Backend rejects admin mutation of the signed-in user's own Employee record with `self_hr_record_edit_not_allowed`. | Employee Detail redesign must preserve this backend rule even when action controls are visible for other records. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | ACCESS-001 RESOLVED | None | Add UI handling for stable error code. | Wave 3
EV-020 | Attendance dashboard | Attendance reporting already includes tenant-scoped identity, department, repeated lateness totals/minutes, 90-day trend and department rollups. | Attendance dashboard Stitch concept can reuse existing dashboard endpoint/data and extend adjustment workflow separately. | High | DEVELOPMENT_DISCREPANCIES_AND_LIMITATIONS.md | RES-035 RESOLVED | None | Reuse existing metrics; avoid invented indicators. | Wave 3

## Route Reconciliation
Route Reconciliation — Current Checkout vs Stitch
Recommendation: preserve current canonical route families for Phase 2 unless there is a compelling product reason to migrate. Stitch route labels are presentation references, not a mandate to churn URLs.
Area | Current Verified Route Family | Stitch / Proposed Route | Decision | Migration Type | Why | Frontend Action | Backend Impact | Screen IDs / Concepts | Confidence | Source
Home / role landing | `/`, `/dashboard` | `/home`, `/executive`, `/insights` | KEEP current route family initially; implement role-aware routing/composition inside existing landing/dashboard structure. | KEEP + optional aliases later | Minimizes route churn while preserving executive/operational distinctions. | Map Stitch Executive/Insights/Home components into current route structure; optionally add redirects after stable release. | None beyond dashboard response extensions. | Home, Executive Dashboard, Insights | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
HR employees | `/hr/employees` | `/employees` | KEEP `/hr/employees`. | KEEP | Current route is established and module-namespaced. | Apply Stitch Employee Directory/Detail design to current HR routes. | None/extend existing employee APIs. | Employee Directory, Employee Detail | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Self Service | `/me`, `/me/profile`, `/me/leave`, `/me/attendance`, `/me/payslips`, `/me/documents`, `/me/emergency-contacts` | `/my-workspace/...` | KEEP `/me/*` for Phase 2 implementation; consider friendly aliases only after rollout. | KEEP | Existing App Router and guards are wired; route rename adds risk with little domain value. | Restyle/recompose current self-service pages using Stitch references. | Reuse existing self-service APIs. | Employee Home, My Profile/Documents/Leave/Attendance/Payslips | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Leave admin | `/leave/dashboard`, `/leave/requests`, `/leave/policies`, `/leave/calendar` | `/leave`, `/leave/requests/:id/review` | KEEP route family; ADD review detail subroute if missing. | KEEP/EXTEND | Current route family is explicit and complete. | Redesign dashboard; wire review page under current request route family. | Extend review/policy-check endpoints only as needed. | Leave Dashboard, Request Review | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Attendance | `/attendance/dashboard`, `/attendance/adjustments`, plus scheduling routes | `/attendance`, `/attendance/adjustments/:id` | KEEP current family; extend adjustment detail. | KEEP/EXTEND | Existing scheduling/attendance surface is broad. | Use Stitch visuals in current pages; add governed review detail where absent. | Extend adjustment workflow. | Attendance Dashboard, My Attendance, Adjustment Review | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Payroll | `/payroll`, `/payroll/runs`, `/payroll/payslips`, etc. | `/payroll`, `/payroll/runs/:id` | KEEP current route family. | KEEP/EXTEND | Already supports controlled run lifecycle and typed APIs. | Apply Stitch workspace/run detail; add exception UI. | Extend existing run validation/exception actions rather than parallel payroll. | Payroll Workspace, Run Detail, My Payslips | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Accounting AP | `/accounting/payables` | `/accounting/ap` | KEEP `/accounting/payables` initially. | KEEP | Existing current route and contracts already exist. | Use Stitch AP design on current path; optional alias `/accounting/ap` later. | No new domain; extend approval/bulk controls. | AP overview, Vendor Bill, bulk governance | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Accounting AR | `/accounting/receivables` | `/accounting/ar` | KEEP `/accounting/receivables`. | KEEP | Existing current route. | Restyle current receivables surfaces. | Extend collections/reminder actions only if approved. | AR overview, Customer Invoice | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Bank / cash | `/accounting/banking` | `/accounting/bank-reconciliation` | KEEP `/accounting/banking`; add reconciliation subroute under it if needed. | KEEP/EXTEND | Current cash/bank domain already exists. | Implement reconciliation workspace within banking family. | New reconciliation session/match models may be needed. | Bank Reconciliation concepts | Medium-High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Accounting reports | `/accounting/reports` | `/accounting/financial-reports` | KEEP `/accounting/reports`; distinguish formal financial statements within page/subroutes. | KEEP/EXTEND | Avoid duplicate report taxonomies. | Apply Financial Reports Stitch designs to accounting reports area. | Extend report definitions/parameters as needed. | Financial Reports library/detail | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Cross-module reports | `/reports/dashboard` | `/reports` | KEEP `/reports/dashboard` initially; catalogue may become `/reports` after deliberate migration. | KEEP/EXTEND | Current reports route exists; catalogue is Phase 2 depth. | Build catalogue progressively without breaking existing links. | Saved config/sharing/schedule models later. | Reports & Analytics | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md
Approvals | `/approvals` | `/approvals` | KEEP. | KEEP/EXTEND | Already canonical. | Merge S064/S066 variants into one inbox. | Extend approval workflow depth only where needed. | Approvals variants | High | ERGONX_UI_AND_FRONTEND_BACKEND_CONTEXT.md

## API Reconciliation
API Reconciliation — Proposed vs Verified
Verified capabilities use current checkout/source evidence. Exact paths marked SCHEMA-VERIFY should be confirmed directly against `openapi-schema.yml` before Codex changes clients.
Contract ID | Capability | Earlier Proposed Contract | Verified Current State | Reconciled Status | Codex Instruction | Exact Path Status | Backend Work | Frontend Work | Wave | Source | Notes
API-R001 | Authentication | `/auth/login`, `/auth/refresh`, `/auth/me` | Verified existing endpoints under `/api/v1/`. | EXISTING | Reuse existing auth adapter/BFF; do not create alternate login API. | VERIFIED | Email OTP only is new. | Security UI + email OTP challenge UX. | Wave 2 | Auth/onboarding specification | BFF cookies are latest resolved session architecture.
API-R002 | Institution context | Proposed `/me/context/` | Current flow uses memberships, `/auth/bootstrap/`, `/institutions/current/`, `/institutions/memberships/`. | SUPERSEDE PROPOSAL | Delete proposed `/me/context/` requirement from contract. Extend bootstrap only if new dashboard-routing fields are missing. | VERIFIED capability; exact bootstrap path documented | Possible bootstrap payload extension only. | Consume effective permissions/modules. | Wave 2 | UI/backend context + auth spec | X-Institution-ID is selector only.
API-R003 | Executive dashboard | Proposed new `/dashboards/executive/` | Endpoint already exists and was hardened to respect enabled modules; ledger rollups/currency present. | EXISTING/EXTEND | Extend existing serializer/view only for approved Phase 2 metrics. | VERIFIED | Add fields only where concept needs real supported data. | Redesign against existing response. | Wave 3 | Discrepancy register | Do not create second executive dashboard service.
API-R004 | Finance dashboard | Not explicitly separated in draft pack | `/api/v1/dashboards/finance/` exists with posted-bank-ledger rollups. | EXISTING | Reuse for finance/Insights where appropriate. | VERIFIED | Only extend if new metrics require it. | Visual integration. | Wave 3/6 | Discrepancy register | Not a full indirect cash-flow statement.
API-R005 | Universal search | Proposed `/search/` | Tenant-aware global search and typed universal-search adapter already exist; route hints come from backend. | EXISTING/EXTEND | Locate exact OpenAPI operation; reuse result contract and add facets/saved-search layer separately. | SCHEMA-VERIFY | Saved searches are new if desired. | Implement Stitch search UX. | Wave 2 | UI/backend context | Authorize before retrieval remains mandatory.
API-R006 | Notifications | Proposed new notification list/preferences system | Notifications domain, route hints and schema support already exist; top-bar/behavior depth needs confirmation. | EXISTING/EXTEND | Reuse current notifications endpoint/model; add recipient read/archive/preferences only if absent. | SCHEMA-VERIFY | Potential recipient/preference extensions. | Build full center on existing domain. | Wave 2 | Discrepancy register + UI context | Do not duplicate notification model.
API-R007 | TOTP MFA | Phase 2 security center | TOTP MFA setup/confirm/disable + login challenge already implemented. | EXISTING | Preserve current MFA contract. | SCHEMA-VERIFY | None for TOTP. | Restyle security UI. | Wave 2 | Discrepancy register UI-003 | Email OTP is additive.
API-R008 | Email OTP | Proposed challenge/verify endpoints | No current evidence of email OTP feature. | NEW | Add explicit challenge/verify operations to accounts/security domain; document in OpenAPI. | NEW | Challenge model/service/rate limiting/audit. | Add MFA choice/login challenge UI. | Wave 2 | User decision + current evidence | SMS stays excluded.
API-R009 | Session management | Proposed active sessions + revoke | BFF HttpOnly-cookie session boundary exists; active-session listing/revocation not evidenced. | NEW/EXTEND | Implement session/token-family tracking compatible with BFF cookies. | NEW | Session registry/revocation. | Security center active-session UI. | Wave 2 | PWA-002 resolution | Never expose raw token values.
API-R010 | Reports export | Proposed richer report export | Current report endpoints export CSV only. | EXISTING + NEW FORMAT LATER | Keep CSV. Introduce XLSX/PDF exporters only as explicit Phase 2 capability and then expose buttons. | VERIFIED limitation | Renderer/job/storage if added. | Match UI to supported formats. | Wave 7/8 | REPORT-001 | Do not fake export formats.
API-R011 | Import/export jobs | Proposed batch/background infrastructure | ImportJob/ExportJob/BackgroundJob already exist with explicit handlers. | EXISTING/EXTEND | Reuse infrastructure for bank statement import and later batch jobs. | SCHEMA-VERIFY | Add typed handlers. | Progress/status UI where needed. | Wave 6/7 | OPS-001 | Unregistered types fail visibly.
API-R012 | AP/AR/Expenses | Draft pack treated as extend/new depending feature | Accounting core + AP/AR/cash/expenses are delivered with documented limitations. | EXISTING/EXTEND | Inspect current accounting API contract and extend actions only; do not rebuild domains. | SCHEMA-VERIFY | Phase 2 workflow depth only. | Apply Stitch redesign. | Wave 6 | Module completion gate | Expenses is current capability.
API-R013 | Recruitment | Draft pack adds JobRequisition/evaluations | Internal ATS exists; JobRequisition target is explicitly planned but not proven present. | EXISTING + NEW DOMAIN EXTENSION | Reuse Candidate/Application/Interview/Offer models; add JobRequisition only after actual recruitment model inspection. | SCHEMA-VERIFY + NEW | Requisition + richer evaluation if absent. | Rework existing recruitment pages. | Wave 4 | Recruitment limitation + auth spec §11 | Public portal remains later.
API-R014 | Attendance dashboard | Draft planned metrics | Current dashboard already provides repeated lateness, minutes, 90-day trend, department rollups. | EXISTING/EXTEND | Reuse dashboard response; add adjustment-specific endpoints only. | VERIFIED capability | Adjustment workflow may be new. | Redesign dashboard + review flow. | Wave 3 | RES-035 | No invented metrics.

## Security-PWA Reconciliation
Security & PWA Reconciliation
This sheet resolves conflicting older and later project documents by applying the latest dated discrepancy resolutions as the current authority.
Item | Older Document State | Latest Resolved State | Authoritative Decision | Phase 2 Action | Risk if Ignored | Status | Wave | Evidence | Codex Rule
PWA assets | Sep-20 context said manifest/service worker/offline route absent. | Sep-22 PWA-001 resolution says manifest, worker, offline route and registration were added and smoke-tested. | Treat PWA as implemented with safe application-shell-only caching. | Preserve cache exclusions while redesigning responsive shell. | Reintroducing API/navigation caching could persist sensitive tenant data. | RESOLVED CURRENT | Wave 1 | PWA-001 resolution | Never cache API responses, exports, JWTs, selected institution or operational tenant data; never queue writes offline.
Browser tokens | Sep-20 context said access/refresh JWTs stored in local storage. | Sep-22 PWA-002 resolution says same-origin BFF stores access/refresh in HttpOnly SameSite cookies; client no longer emits Authorization header. | Treat BFF/HttpOnly cookie architecture as current. | Build active-session management on top of BFF/session families. | A redesign that returns bearer tokens to JS regresses security. | RESOLVED CURRENT | Wave 2 | PWA-002 resolution | Do not reintroduce JS-readable access/refresh tokens.
TOTP MFA | Older docs already described optional MFA. | UI-003 resolved confirms TOTP setup/confirm/disable + login challenge. | Keep TOTP. | Add email OTP as second supported factor. | Duplicating/replacing TOTP wastes working implementation. | EXISTING | Wave 2 | UI-003 | Extend current accounts security flow.
Email OTP | Not evidenced as implemented. | User has selected email OTP because no reliable SMS provider. | Add email OTP only. | Implement challenge hash, expiry, attempts, resend cooldown, throttling, audit and masking. | Weak OTP controls create brute-force/account-takeover risk. | NEW | Wave 2 | User decision + current evidence | No SMS/recovery-phone verification UI.
Module gating | Client guards exist; Django final authority. | Same; backend module/permission gates remain required. | Preserve both UI and backend enforcement. | Ensure redesigned navigation uses bootstrap effective permissions/modules. | Hiding links without server denial causes data exposure. | EXISTING | All | UI/backend context + auth spec | moduleEnabled AND permission; distinguish module_disabled vs permission_denied.

## Gate Reconciliation
Wave 0 Gate Reconciliation
Status after source-based reconciliation. Gates marked PARTIAL still require direct repository/OpenAPI inspection before they can be closed.
Gate | Previous Status | Reconciled Status | What Is Now Proven | What Still Requires Direct Code Inspection | Owner | Blocker Level | Next Action
G0-01 Routes | Not Started | PARTIAL | Current principal route families documented across all modules. | Exact 106-page route inventory and post-Sep20 changes. | Frontend Lead | Medium | Export actual Next.js route tree and diff against Stitch map.
G0-02 API/OpenAPI | Not Started | PARTIAL | OpenAPI validates zero errors/warnings; several endpoint families verified. | Exact operation paths for search/notifications/workflows/accounting/recruitment. | Backend Lead | High | Provide/mount `openapi-schema.yml` or repository; mechanically diff API Contracts sheet.
G0-03 Permissions | Not Started | PARTIAL | Role set and backend-authoritative permission/module model verified; Recruitment permission namespace proposed. | Exact current permission codes across all existing modules. | Security/Backend | High | Extract permissions from backend enums/seed/OpenAPI/docs.
G0-04 Lifecycles | Not Started | PARTIAL | Finalized payroll/posted journal immutability and explicit action endpoints verified. | Exact existing states for Leave, AttendanceAdjustment, Expenses, Recruitment/Offers. | Domain Leads | High | Inspect serializers/services/state enums.
G0-05 Approval engine | Not Started | PARTIAL | Cross-module approvals/workflow APIs exist; deeper configurable engine still Phase 2. | Current workflow models/triggers/delegation/escalation support. | Architecture/Backend | High | Inspect `workflows` app and integration contract.
G0-06 Email OTP | Not Started | DESIGN READY | TOTP existing; email OTP is approved Phase 2 factor; SMS excluded. | Concrete endpoint/model design and security parameters. | Security | High | Implement secure email OTP contract after architecture review.
G0-07 Expense-to-GL | Not Started | PARTIAL | Expenses and accounting core exist; payroll-to-accounting uses explicit mappings/fail-closed behavior. | Current expense posting mapping model/actions and settlement constraints. | Accounting/Backend | High | Inspect accounting expense services and endpoint contract.
G0-08 Ghana payroll | Not Started | PARTIAL | Open statutory/model gaps and fail-closed safeguards are fully documented. | Any new legal/accounting validation since latest register. | Payroll/Research | High | Carry forward existing open items; do not guess values.
G0-09 Stitch mapping | Not Started | COMPLETE | All 66 Stitch screens normalized and mapped; variants identified. | Only final UI frame selection/merge decisions where multiple variants exist. | Design/Frontend | Low | Use master manifest/variant index.
G0-10 Test strategy | Not Started | PARTIAL | Existing regression, PostgreSQL, OpenAPI and production smoke evidence exists. | Phase 2-specific E2E matrix for new workflows. | QA/Engineering | Medium | Draft critical-path tests per wave.
G0-11 Module dependencies | Not Started | PARTIAL | CORE_HR foundational; backend persists module selection and distinguishes module disabled vs permission denied. | Exact dependency rules in current code for Reports/Payroll/Accounting interactions. | Backend/Frontend | Medium | Inspect InstitutionModule/dependency service.
G0-12 Audit taxonomy | Not Started | PARTIAL | Shared AuditLog is established; structured audit UI exists; significant transitions already emit audit/notifications. | Exact Phase 2 event names/payloads for new workflows. | Security/Audit | Medium | Define new event taxonomy alongside each Phase 2 domain extension.

## Immediate Codex Queue
Immediate Codex Preflight Queue
These are the repository-inspection tasks Codex should perform before implementation. They are intentionally codebase-verification tasks, not feature coding.
Order | Task | Repository Targets | Expected Output | Gate Closed | Must Not Change | Risk | Owner | Status
1 | Export actual Next.js route tree and map each ERGX-S screen to current page. | `ergonx-frontend/src/app/**/page.tsx`, navigation config | Route diff: KEEP / RESTYLE / ADD / REDIRECT / DEFER | G0-01 | No route renames yet. | Medium | Frontend | Ready
2 | Generate/read current OpenAPI schema and diff against API contract inventory. | `openapi-schema.yml`, `/api/v1/schema/`, `config/v1_urls.py` | Endpoint matrix: EXISTING / EXTEND / NEW / SUPERSEDE | G0-02 | Do not add endpoints during inventory pass. | High | Backend | Ready
3 | Extract all current permission codes and role defaults. | Permission models/seeds, bootstrap serializer, docs | Permission matrix keyed to actual codes | G0-03 | Do not authorize from display role names. | High | Security/Backend | Ready
4 | Extract domain state enums and action endpoints for Payroll, Journal, Leave, Attendance, Expenses, Recruitment. | models/serializers/services/views + module contracts | Lifecycle matrix using actual states/transitions | G0-04 | Do not rename states merely to match Stitch labels. | High | Domain leads | Ready
5 | Inspect current workflows/approvals domain. | workflow models/views/services/contracts | Current trigger/stage/assignee/delegation/escalation capability map | G0-05 | Do not build generic no-code engine yet. | High | Backend/Architecture | Ready
6 | Inspect Expenses current posting and settlement flow. | accounting expense models/services/views/tests | Expense gap matrix vs Phase 2 target | G0-07 | Do not hard-code GL accounts. | High | Accounting | Ready
7 | Extract module dependency rules. | institution module/dependency services + guards | Dependency matrix and disabled-module response codes | G0-11 | Do not make UI dependency the security mechanism. | Medium | Platform | Ready
8 | Build Phase 2 audit-event catalogue for only new/extended mutations. | audit helpers + existing action event patterns | Event code/payload table | G0-12 | Do not duplicate existing audit events. | Medium | Security/Audit | Ready
9 | Draft Wave 2–7 test matrix after gaps are known. | tests + CI configuration | Critical path unit/integration/E2E/security matrix | G0-10 | Do not lower existing test gates. | Medium | QA | Blocked by 2–8